HIMP Product Roadmap

Phases 12–16

Version 1.1.0 | Updated through Phase 12.4 production verification | 2026-08-20

# 1. Roadmap Purpose

With the Phase 9–11 platform, production, PostgreSQL, scheduler, recovery, reporting, logging, and operational foundations established, the HIMP product roadmap focuses on operator usefulness, operational intelligence, automation value, orchestration UX, notifications, and lifecycle operations. This revision records actual progress through Phase 12.4 and preserves the remaining roadmap.

# 2. Development Rules

One bounded subsystem per subphase.

Build each coherent slice end-to-end before running the slice regression.

Run focused/full regression, compileall, and git diff --check at the end of the slice.

Production validation remains part of Definition of Done.

Create a clear Git checkpoint for each completed subphase where practical.

Reuse existing scheduler, health, execution, remediation, reporting, and persistence infrastructure.

Do not create parallel subsystems or perform unrelated production refactors.

Prefer deterministic and explainable operational intelligence before predictive/AI behavior.

# 3. Roadmap Summary

| Phase | Focus | Estimated Effort | Current Status |
| --- | --- | --- | --- |
| 12 | Operational Intelligence | 27–47 hrs | IN PROGRESS — 12.1–12.4 complete |
| 13 | Automation Intelligence | 20–35 hrs | PLANNED |
| 14 | Workflow & Orchestration UX | 15–25 hrs | PLANNED |
| 15 | Administration & Notifications | 15–25 hrs | PLANNED |
| 16 | Platform Lifecycle & Advanced Operations | 15–30 hrs | PLANNED |
|  | Potential total | 92–162 hrs |  |

# 4. Phase 12 — Operational Intelligence

Status: IN PROGRESS. Phase 12 turns HIMP's existing inventory, plugin health, host health, history, execution, scheduler, storage, and relationship data into a coherent operational view.

## 12.1 — Health Model Consolidation (4–7h)

Status: COMPLETE.

Define the canonical health contract; clarify the relationship between plugin health and infrastructure health; reduce contradictory presentation without rewriting the health system.

## 12.2 — Scheduled Plugin Health (3–5h)

Status: COMPLETE.

Use the existing scheduler for configurable plugin-health refreshes, prevent overlap, record results, expose last/next refresh, and retain manual execution.

## 12.3 — Host Storage Capacity Intelligence (5–8h)

Status: COMPLETE.

Collect and display per-host/per-filesystem capacity: mount point, total, used, free, percent used, and last checked. Provide utilization visibility, dashboard summaries, host detail views, configurable WARNING/CRITICAL thresholds, and stateful alert transitions.

### Storage Visualization and Alert Contract

pve01 /             56%  18 GB free
pve01 /var/lib/vz  78% 220 GB free
automation /        64%   9 GB free
himpdb01 /          83%   7 GB free  WARNING

Notification behavior remains stateful: crossing the warning threshold creates a warning event; remaining above the threshold does not repeatedly notify; crossing the critical threshold creates an escalation event; returning below the configured warning threshold creates a recovery event.

## 12.4 — Infrastructure Relationships (5–8h)

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 12.4 established an explicit, deterministic infrastructure-relationship contract before topology presentation. Git-managed configuration is authoritative; PostgreSQL asset_relationships is the synchronized operational representation.

Canonical entity vocabulary: application, host, service, database, dns, storage, backup.

Canonical relationship vocabulary: runs_on, depends_on, uses, stores_on, backed_up_by, resolves_through, provides.

Relationship validation rejects empty values, unsupported entity/relationship types, self-relationships, and duplicate configured relationships.

Deterministic reconciliation adds missing configured relationships, preserves unchanged relationships, and removes obsolete managed relationships.

Forward source lookup and reverse target lookup are implemented for later dependency/impact analysis.

Authenticated relationship read APIs are live; reconciliation is admin-only.

No PostgreSQL schema migration was required; the existing asset_relationships schema was retained.

### Phase 12.4 Production Relationship State

application:himp --depends_on--> database:himp
application:himp --runs_on-----> host:automation.server.arpa
database:himp    --runs_on-----> host:himpdb01.server.arpa

Initial production reconciliation added exactly three relationships. A second reconciliation proved idempotence: configured=3, added=0, removed=0, unchanged=3, total=3. Direct PostgreSQL verification confirmed exactly three rows.

### Phase 12.4 API Contract

GET /api/relationships

GET /api/relationships/source/{source_type}/{source_id}

GET /api/relationships/target/{target_type}/{target_id}

POST /api/relationships/reconcile — admin-only

Unauthenticated GET and POST requests returned HTTP 401. After refreshing the HIMP admin session, all four live API checks returned HTTP 200. The source lookup for application:himp returned two relationships, and the reverse target lookup for database:himp correctly returned the HIMP application dependency.

### Phase 12.4 Regression Finding and Correction

The full regression gate exposed a real PostgreSQL lifecycle defect unrelated to relationship semantics: long-lived database facades could retain a reference to a shared pool after FastAPI shutdown closed and removed that pool. PostgreSQLDatabase now reacquires the current shared pool only when its cached pool is closed, preserving explicit shutdown cleanup and existing test seams.

Dedicated lifecycle regression coverage was added. The final full regression completed with 893 passing tests. compileall and git diff --check passed.

### Phase 12.4 Release Checkpoint

Branch:       feature/plugin-sdk
Commit:       6ca4aeefbdf968dbaa4b9f90c63f435a91b2c9ff
Subject:      feat: add infrastructure relationship management
LOCAL:        6ca4aeefbdf968dbaa4b9f90c63f435a91b2c9ff
REMOTE:       6ca4aeefbdf968dbaa4b9f90c63f435a91b2c9ff
DEPLOYED:     6ca4aeefbdf968dbaa4b9f90c63f435a91b2c9ff
Regression:   893 passed
compileall:   PASS
diff check:   PASS
HIMP service: ACTIVE
Listener:     0.0.0.0:9347
Worktree:     CLEAN / synchronized

## 12.5 — Dependency & Impact Analysis (4–7h)

Status: NEXT.

Use the live forward/reverse relationship contract to answer operational questions such as what depends on a host or service, what could be affected by a failure, and which unhealthy dependency may explain a problem. Reuse the Phase 12.4 relationship model rather than creating a second dependency model.

## 12.6 — Health Correlation & Trends (4–8h)

Status: PLANNED.

Use historical data for deterministic analysis of repeated failures, flapping, degradation frequency, health duration, correlated failures, and recurring unhealthy periods.

## 12.7 — Phase 12 Production Gate (2–4h)

Status: PLANNED.

Run regression, compileall, diff validation, production deployment, browser/API validation, scheduler validation, PostgreSQL validation, and checkpoint documentation.

# 5. Phase 13 — Automation Intelligence

## 13.1 — Remediation Recommendations (5–8h)

Translate known health conditions into evidence-backed recommended operator actions; no autonomous execution initially.

## 13.2 — Approval Queue (4–6h)

Central operator view for remediation actions requiring approval, including target, reason, risk, approve/deny, and audit history.

## 13.3 — Remediation Scheduling (3–5h)

Allow approved remediation to run later using the existing scheduler; no second scheduling subsystem.

## 13.4 — Verification Improvements (3–5h)

Strengthen post-remediation health recheck, expected-condition confirmation, and execution closure.

## 13.5 — Low-Risk Autonomous Remediation (5–8h)

Only after preceding controls are production proven; use explicit ALLOW_AUTOMATIC / REQUIRE_APPROVAL / DENY policy with fail-closed safety.

## 13.6 — Production Gate (2–4h)

Regression, deployment, production validation, and documentation.

# 6. Phase 14 — Workflow & Orchestration UX

Improve operator understanding and control of the existing workflow engine rather than building a replacement execution framework.

Workflow execution timeline with steps, timestamps, durations, and status.

Operator-readable failure analysis including failed step, target, return code/error, and prior successful step.

Safe retry/replay controls that distinguish retrying an operation, rerunning a workflow, and any supported resume behavior.

Improved workflow history and execution-detail navigation.

Production gate and documentation.

# 7. Phase 15 — Administration & Notifications

Introduce a reusable notification framework that routes operational events without coupling individual monitoring features to specific transports.

Notification event model and routing policy.

Configurable destinations such as email, Microsoft Teams, Slack, or other approved transports.

Severity, suppression, acknowledgement, escalation, and recovery semantics.

Storage events explicitly supported: STORAGE_WARNING, STORAGE_CRITICAL, STORAGE_RECOVERED.

Health, automation, remediation, backup, and other operational event sources can later reuse the same framework.

Administrative configuration UI, authorization, audit history, and production gate.

# 8. Phase 16 — Platform Lifecycle & Advanced Operations

Reserve Phase 16 for product lifecycle capabilities justified by real operational needs after Phases 12–15. Candidate work includes richer maintenance-window controls, lifecycle visibility, advanced operational reporting, capacity forecasting after sufficient history exists, and other cross-platform operational improvements. Scope should be approved from production evidence rather than implemented merely because it appears on the roadmap.

# 9. Immediate Starting Point

Begin Phase 12.5 — Dependency & Impact Analysis. First confirm Git branch/status, deployed revision, HIMP service state, PostgreSQL relationship count, and the Phase 12.4 relationship service/API contract. Define one bounded impact-analysis slice that reuses forward and reverse relationship lookups. Do not create a parallel dependency model or topology subsystem.

1. Confirm feature/plugin-sdk is clean and synchronized.
2. Confirm SOURCE == REMOTE == DEPLOYED == 6ca4aee...
3. Confirm HIMP service is active on port 9347.
4. Confirm asset_relationships contains the three production relationships.
5. Review AssetRelationshipService source/target lookup contracts.
6. Define deterministic dependency traversal and impact-result contract.
7. Implement the bounded Phase 12.5 slice end-to-end.
8. Run focused tests, then full regression, compileall, and git diff --check.
9. Commit/push/deploy only after the complete gate passes.

# 10. Roadmap Decision Record

This roadmap intentionally does not reopen completed Phase 9–11 infrastructure work. Storage capacity visibility remains a first-class Phase 12 operational-intelligence feature. Notification transport remains deferred to the shared Phase 15 framework. Phase 12.4 established the explicit relationship foundation required for Phase 12.5 dependency and impact analysis. Predictive/AI analysis remains deferred until deterministic operational intelligence is production-proven.