HIMP Product Roadmap

Phases 12–16

Version 1.35.0 | Phase 16.8.3A inventory-aware operator guidance closure | 2026-09-19

# 1. Roadmap Purpose

With the Phase 9–11 platform, production, PostgreSQL, scheduler, recovery, reporting, logging, and operational foundations established, the HIMP product roadmap focuses on operator usefulness, operational intelligence, automation value, orchestration UX, notifications, and lifecycle operations. This revision records the completed and production-verified Phase 12 Operational Intelligence program and preserves the remaining roadmap beginning with Phase 13.

# 2. Development Rules

One bounded subsystem per subphase.

Build each coherent slice end-to-end before running the slice regression.

Run focused/full regression, compileall, and git diff --check at the end of the slice.

Production validation remains part of Definition of Done.

Create a clear Git checkpoint for each completed subphase where practical.

Reuse existing scheduler, health, execution, remediation, reporting, and persistence infrastructure.

Do not create parallel subsystems or perform unrelated production refactors.

Prefer deterministic and explainable operational intelligence before predictive/AI behavior.

# 3. Roadmap Summary

| Phase | Focus | Estimated Effort | Current Status |
| --- | --- | --- | --- |
| 12 | Operational Intelligence | 27–47 hrs | COMPLETE / PRODUCTION VERIFIED |
| 13 | Automation Intelligence | 20–35 hrs | COMPLETE / PRODUCTION VERIFIED |
| 14 | Workflow & Orchestration UX | 15–25 hrs | COMPLETE / PRODUCTION VERIFIED |
| 15 | Administration & Notifications | 15–25 hrs | COMPLETE / PRODUCTION VERIFIED |
| 16 | Platform Lifecycle & Advanced Operations | 15–30 hrs | ACTIVE — 16.1, 16.3, 16.4, 16.5, 16.6, 16.7, and 16.8.1–16.8.3 COMPLETE / PRODUCTION VERIFIED |
|  | Potential total | 92–162 hrs |  |

# 4. Phase 12 — Operational Intelligence

Status: COMPLETE / PRODUCTION VERIFIED. Phase 12 turns HIMP's existing inventory, plugin health, host health, history, execution, scheduler, storage, and relationship data into a coherent operational view.

## 12.1 — Health Model Consolidation (4–7h)

Status: COMPLETE.

Define the canonical health contract; clarify the relationship between plugin health and infrastructure health; reduce contradictory presentation without rewriting the health system.

## 12.2 — Scheduled Plugin Health (3–5h)

Status: COMPLETE.

Use the existing scheduler for configurable plugin-health refreshes, prevent overlap, record results, expose last/next refresh, and retain manual execution.

## 12.3 — Host Storage Capacity Intelligence (5–8h)

Status: COMPLETE.

Collect and display per-host/per-filesystem capacity: mount point, total, used, free, percent used, and last checked. Provide utilization visibility, dashboard summaries, host detail views, configurable WARNING/CRITICAL thresholds, and stateful alert transitions.

### Storage Visualization and Alert Contract

pve01 /             56%  18 GB free
pve01 /var/lib/vz  78% 220 GB free
automation /        64%   9 GB free
himpdb01 /          83%   7 GB free  WARNING

Notification behavior remains stateful: crossing the warning threshold creates a warning event; remaining above the threshold does not repeatedly notify; crossing the critical threshold creates an escalation event; returning below the configured warning threshold creates a recovery event.

## 12.4 — Infrastructure Relationships (5–8h)

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 12.4 established an explicit, deterministic infrastructure-relationship contract before topology presentation. Git-managed configuration is authoritative; PostgreSQL asset_relationships is the synchronized operational representation.

Canonical entity vocabulary: application, host, service, database, dns, storage, backup.

Canonical relationship vocabulary: runs_on, depends_on, uses, stores_on, backed_up_by, resolves_through, provides.

Relationship validation rejects empty values, unsupported entity/relationship types, self-relationships, and duplicate configured relationships.

Deterministic reconciliation adds missing configured relationships, preserves unchanged relationships, and removes obsolete managed relationships.

Forward source lookup and reverse target lookup are implemented for later dependency/impact analysis.

Authenticated relationship read APIs are live; reconciliation is admin-only.

No PostgreSQL schema migration was required; the existing asset_relationships schema was retained.

### Phase 12.4 Production Relationship State

application:himp --depends_on--> database:himp
application:himp --runs_on-----> host:automation.server.arpa
database:himp    --runs_on-----> host:himpdb01.server.arpa

Initial production reconciliation added exactly three relationships. A second reconciliation proved idempotence: configured=3, added=0, removed=0, unchanged=3, total=3. Direct PostgreSQL verification confirmed exactly three rows.

### Phase 12.4 API Contract

GET /api/relationships

GET /api/relationships/source/{source_type}/{source_id}

GET /api/relationships/target/{target_type}/{target_id}

POST /api/relationships/reconcile — admin-only

Unauthenticated GET and POST requests returned HTTP 401. After refreshing the HIMP admin session, all four live API checks returned HTTP 200. The source lookup for application:himp returned two relationships, and the reverse target lookup for database:himp correctly returned the HIMP application dependency.

### Phase 12.4 Regression Finding and Correction

The full regression gate exposed a real PostgreSQL lifecycle defect unrelated to relationship semantics: long-lived database facades could retain a reference to a shared pool after FastAPI shutdown closed and removed that pool. PostgreSQLDatabase now reacquires the current shared pool only when its cached pool is closed, preserving explicit shutdown cleanup and existing test seams.

Dedicated lifecycle regression coverage was added. The final full regression completed with 893 passing tests. compileall and git diff --check passed.

### Phase 12.4 Release Checkpoint

Branch:       feature/plugin-sdk
Commit:       6ca4aeefbdf968dbaa4b9f90c63f435a91b2c9ff
Subject:      feat: add infrastructure relationship management
LOCAL:        6ca4aeefbdf968dbaa4b9f90c63f435a91b2c9ff
REMOTE:       6ca4aeefbdf968dbaa4b9f90c63f435a91b2c9ff
DEPLOYED:     6ca4aeefbdf968dbaa4b9f90c63f435a91b2c9ff
Regression:   893 passed
compileall:   PASS
diff check:   PASS
HIMP service: ACTIVE
Listener:     0.0.0.0:9347
Worktree:     CLEAN / synchronized

## 12.5 — Dependency & Impact Analysis (4–7h)

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 12.5 added deterministic, read-only dependency traversal and reverse-impact analysis over the Phase 12.4 canonical relationship graph. The implementation reuses AssetRelationshipService and does not introduce a parallel dependency model, graph database, schema migration, or topology storage layer.

Dependency traversal follows outgoing source-to-target relationship edges and answers “What does this asset depend on?”

Impact traversal follows incoming edges in reverse and answers “What depends on this asset?” and “What could be affected if this asset fails?”

Breadth-first traversal provides deterministic shortest discovered paths, depth tracking, and cycle protection.

Each reachable asset is returned once with entity type, entity ID, depth, the relationship used to reach it, and the complete relationship path from the requested root.

Optional max_depth limits analysis to direct or bounded transitive relationships without changing graph semantics.

Both new API routes inherit the existing authenticated-session boundary. Phase 12.5 remains read-only against asset_relationships.

### Phase 12.5 Live Production Results

Dependencies of application:himp:
depth 1  database:himp via depends_on
depth 1  host:automation.server.arpa via runs_on
depth 2  host:himpdb01.server.arpa via runs_on

Impact of host:himpdb01.server.arpa:
depth 1  database:himp via runs_on
depth 2  application:himp via depends_on

### Phase 12.5 API Contract

GET /api/dependencies/{entity_type}/{entity_id}

GET /api/impact/{entity_type}/{entity_id}

Both routes accept optional max_depth >= 1.

Unauthenticated production requests returned HTTP 401; authenticated full and depth-limited requests returned HTTP 200.

### Phase 12.5 Validation and Release Checkpoint

Branch:       feature/plugin-sdk
Commit:       b0650cbbe74be0ce7ae77761b369dd97446f7011
Subject:      feat: add dependency impact analysis
LOCAL:        b0650cbbe74be0ce7ae77761b369dd97446f7011
REMOTE:       b0650cbbe74be0ce7ae77761b369dd97446f7011
DEPLOYED:     b0650cbbe74be0ce7ae77761b369dd97446f7011
Focused:      49 passed
Regression:   913 passed
compileall:   PASS
diff check:   PASS
OpenAPI:      PASS
Production graph analysis: PASS
Production relationship rows: 3 (unchanged)
HIMP service: ACTIVE
Listener:     0.0.0.0:9347
Worktree:     CLEAN / synchronized

## 12.6 — Health Correlation & Trends (4–8h)

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 12.6 added deterministic historical health analysis over HIMP's existing plugin and host health-history stores. The implementation analyzes repeated failures, warnings, state transitions, current streaks, unhealthy percentages, observed unhealthy duration, and bounded flapping behavior without introducing a second persistence layer or predictive/AI behavior. Relationship-aware correlation reuses the Phase 12.5 dependency graph and explicitly distinguishes topology assets that have no persisted host-health history.

### Phase 12.6 Live Production Results

Host analysis for pbs01 returned 260 observations: 259 PASS, 1 FAIL, 0 WARNING, 2 state transitions, 1 flap event, current state HEALTHY, current streak 7, and is_flapping=false. Plugin analysis for technitium returned 6 observations: 4 PASS, 2 WARNING, 0 FAIL, current state HEALTHY, and current streak 4.

Relationship-aware correlation for application:himp returned two reachable hosts. automation.server.arpa is a valid depth-1 topology dependency but currently has no persisted host-health history, so HIMP reports history_available=false and current_state=UNKNOWN. himpdb01.server.arpa is a depth-2 dependency with 5 persisted PASS observations and current_state=HEALTHY. This preserves the distinction between 'known topology asset with no observations' and an unhealthy asset.

### Phase 12.6 API Contract

Authenticated read-only endpoints are available for host analysis, plugin analysis, and relationship-aware correlation under /api/health/analysis. Unauthenticated production requests returned HTTP 401; authenticated production requests returned HTTP 200. Deployment and API validation did not mutate health-history or relationship data.

### Phase 12.6 Validation and Release Checkpoint

Branch:       feature/plugin-sdk
Commit:       d02aa17126b105adb577d86d0c11f5221eb685ef
Subject:      feat: add historical health analysis
LOCAL:        d02aa17126b105adb577d86d0c11f5221eb685ef
REMOTE:       d02aa17126b105adb577d86d0c11f5221eb685ef
DEPLOYED:     d02aa17126b105adb577d86d0c11f5221eb685ef
Focused:      61 passed
Regression:   932 passed
compileall:   PASS
diff check:   PASS
OpenAPI:      PASS
Production health analysis: PASS
Authenticated API validation: PASS
Production plugin-health rows: 27 (unchanged)
Production host-health rows: 11160 (unchanged)
Production relationship rows: 3 (unchanged)
HIMP service: ACTIVE
Listener:     0.0.0.0:9347
Worktree:     CLEAN / synchronized

### Phase 12.6 Operational Follow-up

COMPLETED during Phase 12 closure. automation.server.arpa was added to the infrastructure inventory group through the HIMP web inventory workflow, HIMP service SSH authorization was validated, Ansible ping succeeded, and a direct host-health check persisted a PASS observation. Relationship-aware correlation subsequently reported history_available=true and HEALTHY for the automation host. The production PostgreSQL credential-rotation item remains separately tracked because it is not part of the Phase 12 implementation scope.

## 12.7 — Phase 12 Production Gate (2–4h)

Status: COMPLETE / PRODUCTION VERIFIED.
The final Phase 12 production closure gate passed across regression, deployment state, authentication boundaries, scheduler operation, PostgreSQL state, runtime inventory, Ansible connectivity, relationship analysis, dependency/impact analysis, and historical health correlation.

Final Phase 12 Production Gate
• Clean-environment full regression: 934 passed.
• compileall: PASS; git diff --check: PASS; deployment script syntax: PASS.
• HIMP service: ACTIVE; listener 0.0.0.0:9347; /login HTTP 200.
• Scheduler timer: ACTIVE / waiting; scheduler service correctly inactive between runs; last scheduled_updates execution completed successfully.
• Production counts: 49 inventory hosts, 27 plugin-health rows, 11161 host-health rows, 3 relationship rows, 6 schedules.
• automation.server.arpa is present in the infrastructure CMDB and persistent runtime inventory, Ansible ping succeeds, and host-health history contains a PASS observation.
• Unauthenticated relationship, impact, and health-analysis requests returned HTTP 401; authenticated relationship, dependency, impact, host-analysis, and correlation requests returned HTTP 200.
• Relationship-aware correlation for application:himp reports both related hosts with health history available, HEALTHY, and non-flapping.
• Repository/worktree: CLEAN / synchronized.

Production Corrections Completed During Closure
0d86409d1be6c90e22be2be09cb3db2dcf53b0f4 — fix: support current ansible inventory validation. Removed the unsupported --json argument from ansible-inventory validation and strengthened regression coverage.
cbfbc354e1f6b0584e92e5ee6d4d9ae3688716b1 — fix: preserve runtime inventory across deployments. Git inventory now seeds runtime inventory only when hosts.yml is absent; subsequent deployments preserve web-managed runtime inventory.

Final Phase 12 Release Checkpoint
Branch: feature/plugin-sdk
LOCAL: cbfbc354e1f6b0584e92e5ee6d4d9ae3688716b1
REMOTE: cbfbc354e1f6b0584e92e5ee6d4d9ae3688716b1
DEPLOYED: cbfbc354e1f6b0584e92e5ee6d4d9ae3688716b1
Regression: 934 passed
compileall: PASS
diff check: PASS
Deploy script syntax: PASS
HIMP service: ACTIVE
Listener: 0.0.0.0:9347
Scheduler timer: ACTIVE
Worktree: CLEAN / synchronized

Phase 12 Operational Intelligence is CLOSED. The next product development phase is Phase 13 — Automation Intelligence.

# 5. Phase 13 — Automation Intelligence

Status: COMPLETE / PRODUCTION VERIFIED. Phase 13 converts HIMP's deterministic operational intelligence into controlled, auditable automation assistance while preserving explicit operator authority and fail-closed execution boundaries. Phases 13.1 through 13.6 are complete and production verified.

## 13.1 — Remediation Recommendations (5–8h)

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 13.1 added deterministic, evidence-backed remediation recommendations over the existing health-analysis and dependency-impact services. Recommendation generation is read-only: it does not execute automation, create remediation audit records, or modify infrastructure state.

• Recommendations are derived from persisted host health and relationship/dependency evidence.

• Unhealthy and flapping conditions are translated into operator-readable severity, rationale, evidence, affected assets, dependency path, and recommended action.

• Recommendation output explicitly reports execution_permitted=false and execution_performed=false.

• Authenticated API: GET /api/remediation/recommendations/{entity_type}/{entity_id}.

• Production application:himp validation returned HTTP 200 with zero recommendations because the correlated production hosts were healthy.

• Unauthenticated production access returned HTTP 401.

• Read-only production validation left remediation audit, remediation operation, relationship, and host-health counts unchanged.

### Phase 13.1 Validation and Release Checkpoint

Branch: feature/plugin-sdk

Commit: e519e336cc865a5976829434e99046210a14b6df

Subject: feat: add evidence-backed remediation recommendations

Focused regression: 63 passed

Full regression: 948 passed

compileall: PASS

diff check: PASS

OpenAPI route: PASS

Authenticated production API: HTTP 200

Unauthenticated boundary: HTTP 401

Production safety check: no remediation execution or audit mutation

## 13.2 — Approval Queue (4–6h)

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 13.2 added a durable remediation approval queue and operator UI while keeping approval decisions separate from remediation execution. The queue provides a controlled administrative decision point for recommendations that require authorization.

• A dedicated remediation_approvals persistence model stores recommendation evidence, source/target identity, condition, severity, recommended action, rationale, affected assets, dependency path, requester, decision actor, decision note, and timestamps.

• Approval lifecycle states are PENDING, APPROVED, and DENIED.

• Creation and approve/deny decision routes require administrator authorization; read access remains behind the existing authenticated session boundary.

• Approval decisions are durable and auditable but do not themselves execute remediation.

• The Remediation page now includes an Approval Queue with status filtering, recommendation context, evidence, affected assets, decision notes, and approve/deny controls.

• Existing remediation execution UI remains present and separate; Phase 13.2 does not collapse approval and execution into one action.

• PostgreSQL schema and SQLite-to-PostgreSQL migration inventories were extended for remediation_approvals.

### Phase 13.2 API Contract

• POST /api/remediation/approvals — create approval request; admin-only

• GET /api/remediation/approvals — list/filter approval queue

• GET /api/remediation/approvals/{approval_id} — approval detail

• POST /api/remediation/approvals/{approval_id}/approve — approve; admin-only

• POST /api/remediation/approvals/{approval_id}/deny — deny; admin-only

### Phase 13.2 Validation and Release Checkpoint

Branch: feature/plugin-sdk

Commit: e2fe1e6cd1d7bc9d308cb4dbb046d8426c1a5678

Subject: feat: add remediation approval queue

UI regression: 25 passed

Backend regression: 69 passed

Database regression: 33 passed

Full clean-environment regression: 975 passed

compileall: PASS

diff check: PASS

HIMP service: ACTIVE

Scheduler timer: ACTIVE

Repository/worktree: CLEAN / synchronized

LOCAL = REMOTE = DEPLOYED = e2fe1e6cd1d7bc9d308cb4dbb046d8426c1a5678

## 13.3 — Remediation Scheduling (3–5h)

Status: COMPLETE / PRODUCTION VERIFIED.
Phase 13.3 added one-time scheduling for individually approved remediation while reusing the existing HIMP scheduler process and the existing remediation execution, policy, verification, and audit services. No parallel scheduler or remediation execution framework was introduced.

• Approved remediation now carries a frozen task_id so the executable automation identity is preserved with the approval snapshot.
• A dedicated remediation_schedules persistence model records approval_id, scheduled execution time, lifecycle status, scheduler identity, start/completion timestamps, audit linkage, failure text, and cancellation metadata.
• Schedule lifecycle states are SCHEDULED, RUNNING, COMPLETED, FAILED, and CANCELLED.
• Only APPROVED remediation may be scheduled; PENDING or DENIED approvals fail closed.
• A single approval may have only one remediation schedule record.
• Due schedules are claimed atomically through SCHEDULED → RUNNING so concurrent scheduler invocations cannot execute the same remediation twice.
• Scheduled execution reconstructs the exact approved remediation snapshot rather than regenerating recommendations at execution time.
• Existing remediation policy is re-evaluated at execution time; approval does not bypass a later policy DENY or disabled automation state.
• Cancellation preserves the approval record and leaves a durable operator audit trail.
• Browser-local datetime input is converted to ISO UTC; persistence uses UTC-naive timestamps, while internal naive datetimes are interpreted as host-local before UTC conversion.

Phase 13.3 API Contract
• POST /api/remediation/schedules — create a one-time schedule for an approved remediation; admin-only
• GET /api/remediation/schedules — list/filter remediation schedules
• GET /api/remediation/schedules/{schedule_id} — schedule detail
• POST /api/remediation/schedules/{schedule_id}/cancel — cancel a SCHEDULED item; admin-only

Phase 13.3 Validation and Release Checkpoint
Branch: feature/plugin-sdk
Commit: f004c1019c8f730b6107d7ecf8b8f433f40a8147
Subject: feat: add remediation scheduling
Focused regression: 93 passed
Full regression: 1005 passed
compileall: PASS
diff check: PASS
PostgreSQL backend: VERIFIED
remediation_approvals.task_id: PRESENT
remediation_schedules table: PRESENT
Live API routes: VERIFIED
Post-deployment scheduler execution: VERIFIED
HIMP service: ACTIVE
Scheduler timer: ACTIVE / enabled
Listener: 0.0.0.0:9347
LOCAL = REMOTE = DEPLOYED = f004c1019c8f730b6107d7ecf8b8f433f40a8147
Repository/worktree: CLEAN / synchronized
Production validation found zero active remediation recommendations, zero approvals, and zero schedules; no synthetic production remediation evidence was created solely for smoke testing.

## 13.4 — Verification Improvements (3–5h)

Status: COMPLETE / PRODUCTION VERIFIED.
Phase 13.4 strengthened post-remediation verification so HIMP distinguishes automation execution success from verified remediation outcome. The existing RemediationVerificationService, HostHealthService, HealthAnalysisService, remediation workflow, scheduling service, audit repository, dashboard, and logging surfaces were extended rather than replaced.

• Verification now records explicit status, success, reason, condition, hostname, and bounded evidence.
• Supported deterministic conditions are HOST_UNHEALTHY and HOST_FLAPPING.
• HOST_UNHEALTHY is VERIFIED only when a fresh post-remediation host-health check returns PASS; otherwise it is NOT_VERIFIED.
• HOST_FLAPPING requires a fresh host observation plus bounded historical re-analysis; it is VERIFIED only when fresh health is PASS and the host is no longer classified as flapping.
• Unsupported or insufficiently evaluable conditions return NOT_SUPPORTED rather than being treated as successful.
• Failed automation returns EXECUTION_FAILED and does not perform a misleading health verification.
• Legacy immediate-remediation proposals without an explicit condition retain deterministic fresh-host-health verification for backward compatibility.
• remediation_audit now persists verification_status, verification_success, and verification_evidence independently from execution_success.
• Scheduled remediation reaches COMPLETED only when policy allows execution, automation succeeds, and verification succeeds. Successful execution with NOT_VERIFIED or NOT_SUPPORTED outcome closes the schedule as FAILED while retaining audit linkage.
• Immediate remediation workflow now exposes verification_count, verified_count, and unverified_count.
• Remediation history/detail UI shows Execution and Verification separately, including verification evidence and summary counters.
• Normalized remediation logs treat failed verification as a failed remediation outcome even when the underlying automation execution succeeded.

Phase 13.4 Validation and Release Checkpoint
Branch: feature/plugin-sdk
Commit: 72a09c6120897ee82f703182e2162a28b3940254
Subject: feat: strengthen remediation verification
Focused regression: 97 passed
Full regression: 1022 passed
compileall: PASS
diff check: PASS
PostgreSQL backend: VERIFIED
verification_status column: PRESENT
verification_success column: PRESENT
verification_evidence column: PRESENT
HIMP service: ACTIVE
Listener: 0.0.0.0:9347
Root application response: HTTP 303
Scheduler timer/service path: VERIFIED; forced post-deployment run exited 0/SUCCESS with Due tasks: 0 and Due remediation schedules: 0.
Existing production remediation audit rows: 48; historical verification counters remained zero because Phase 13.4 does not invent outcomes for pre-13.4 records.
LOCAL = REMOTE = DEPLOYED = 72a09c6120897ee82f703182e2162a28b3940254
Repository/worktree: CLEAN / synchronized

## 13.5 — Low-Risk Autonomous Remediation (5–8h)

Status: COMPLETE / PRODUCTION VERIFIED.
Phase 13.5 added a fail-closed autonomous remediation framework without authorizing any production action for automatic execution. The implementation reuses the existing recommendation, policy, execution, verification, audit, approval, scheduler, and operational-dispatcher paths rather than creating a parallel automation subsystem.

• RemediationAutonomyPolicyService provides explicit ALLOW_AUTOMATIC / REQUIRE_APPROVAL / DENY decisions.
• Production defaults to an empty autonomous allowlist; nothing is autonomous unless explicitly mapped and allowlisted.
• Exact target identity, condition, risk class, task identity, enabled state, dependency state, and confirmation requirements are evaluated fail closed.
• Destructive automation is always denied by the autonomous policy.
• Current HOST_UNHEALTHY and HOST_FLAPPING recommendations retain automation=None and therefore remain operator-controlled.
• Recommendation API responses can carry the autonomy decision while remaining read-only and reporting execution_performed=false.
• Approval routing accepts REQUIRE_APPROVAL, rejects DENY, and prevents ALLOW_AUTOMATIC items from incorrectly entering the operator approval queue.
• RemediationExecutionService now accepts an optional exact-target limit so a future eligible update_host action can remain bounded to one host.
• RemediationAutonomousExecutionService re-evaluates the existing execution policy, executes only ALLOW_AUTOMATIC recommendations, requires Phase 13.4 verification, and persists audit evidence.
• RemediationAutonomousWorkflowService summarizes autonomous eligibility, execution, completion, failure, approval-required, and denied outcomes without auto-creating duplicate approval records.
• Scheduled remediation_operations now route through the fail-closed autonomous recommendation workflow instead of the legacy broad remediation workflow.
• The production allowlist remains empty, so the new framework is operationally present but performs zero autonomous remediation.

Phase 13.5 Validation and Release Checkpoint
Branch: feature/plugin-sdk
Commit: 4282dab4a497deee4eb86b53ed732cc72498c3cb
Subject: feat: add low-risk autonomous remediation
Focused regression: 133 passed
Full regression: 1050 passed
compileall: PASS
diff check: PASS
Production HIMP service: ACTIVE
Listener: 0.0.0.0:9347
Root application response: HTTP 303
Autonomous allowlist: {} (empty / fail closed)
Production recommendation count during validation: 0
Automatic eligible count: 0
Executed count: 0
Execution performed: False
Remediation audit rows before/after validation: 48 / 48
Forced scheduler run: 0/SUCCESS; Due tasks: 0; Due remediation schedules: 0
LOCAL = REMOTE = DEPLOYED = 4282dab4a497deee4eb86b53ed732cc72498c3cb
Repository/worktree: CLEAN / synchronized

## 13.6 — Production Gate (2–4h)

Status: COMPLETE / PRODUCTION VERIFIED.
Phase 13.6 completed the final Phase 13 production gate without adding new product behavior. The gate revalidated repository state, deployed release identity, HIMP runtime health, scheduler behavior, PostgreSQL remediation state, autonomous-remediation safety posture, host systemd readiness, regression quality, rollback assets, and closure documentation.

Final Phase 13 Production Gate
• Repository branch feature/plugin-sdk remained clean and synchronized.
• LOCAL = REMOTE = 60ad66f633a9c8d0ae76c0c2ae889f6f061e627d. This commit is documentation-only: docs: close phase 13.5 autonomous remediation.
• DEPLOYED = 4282dab4a497deee4eb86b53ed732cc72498c3cb, the verified Phase 13.5 application release. The LOCAL/REMOTE versus DEPLOYED difference is intentional because the newer commit contains only roadmap documentation.
• HIMP service: ACTIVE / enabled; Restart=always; User/Group=himp:himp; WorkingDirectory=/opt/himp.
• Listener: 0.0.0.0:9347; root application response: HTTP 303.
• HIMP scheduler timer: ACTIVE / enabled. A forced scheduler execution completed with code=exited, status=0/SUCCESS; Due tasks: 0; Due remediation schedules: 0; No scheduled work was due.
• PostgreSQL backend: VERIFIED.
• Remediation audit summary: total=48, allow=24, deny=16, confirmation-required=8, execution-success=24, execution-failure=0. Historical Phase 13.4 verification counters remain zero because pre-13.4 records are not retroactively assigned verification outcomes.
• Approval queue: total=0, pending=0, approved=0, denied=0.
• Remediation schedules: total=0 across SCHEDULED/RUNNING/COMPLETED/FAILED/CANCELLED states.
• Autonomous remediation allowlist: {}. Production recommendation count during the gate: 0; recommendation execution_performed=false. No action is currently authorized for autonomous execution.
• HIMP and scheduler journals contained no warning-or-higher entries during the two-hour production-gate review window.
• Initial systemctl --failed review found two historical host-state entries: a transient August 13 hardening write-denial test and a stale wtmpdb-rotate.timer from an older package/unit layout. The hardening test failure was expected and proved the write restriction; the current wtmpdb package ships wtmpdb-update-boot.service rather than the obsolete timer. Historical failed state was cleared, daemon state reloaded, and the final systemctl --failed result was 0 loaded units. Current wtmpdb-update-boot.service is enabled and active (exited) with status 0/SUCCESS.
• Final full regression: 1050 passed.
• compileall: PASS.
• git diff --check: PASS.
• Deployment script present: scripts/deploy/himp.sh.
• Release/upgrade/rollback runbook present: docs/operations/HIMP_RELEASE_UPGRADE_ROLLBACK.md.
• Final repository status: CLEAN / synchronized.

Phase 13 Automation Intelligence is CLOSED. No Phase 13 production code changes remain. The next product development phase is Phase 14 — Workflow & Orchestration UX.

# 6. Phase 14 — Workflow & Orchestration UX

Improve operator understanding and control of the existing workflow engine rather than building a replacement execution framework.

Workflow execution timeline with steps, timestamps, durations, and status.

Operator-readable failure analysis including failed step, target, return code/error, and prior successful step.

Safe retry/replay controls that distinguish retrying an operation, rerunning a workflow, and any supported resume behavior.

Improved workflow history and execution-detail navigation.

Production gate and documentation.

## 14.1 — Workflow Execution Timeline & Failure Visibility

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 14.1 delivered an operator-readable workflow execution timeline on top of the existing workflow and AutomationService execution framework. The slice preserved the architectural rule that HIMP must not create a second execution engine. Workflow runs now expose persisted workflow state together with correlated automation execution history, step timestamps, durations, status, execution identifiers, and expandable failure detail.

Added workflow execution history/timeline composition and production UI navigation for individual workflow runs.

Added step-level timeline events showing workflow start, automation task execution, workflow completion, timestamps, durations, and status.

Added operator-visible automation execution correlation so a workflow task can link to its persisted automation execution record.

Added failure-detail presentation for failed workflow steps while preserving the existing automation execution evidence.

Production validation exposed a real orchestration defect: WorkflowExecutionService treated the AutomationService execution envelope as successful unless a top-level success field existed.

Commit 74feabd fixed workflow failure propagation by interpreting the normalized nested result.success value while preserving support for the direct success contract.

Regression coverage was added for nested AutomationService failure envelopes and direct success envelopes.

A production validation run then correctly reported WORKFLOW_SUCCESS=False, executed health_check, and marked health_check as the failed task.

The final browser-validated production execution f7236921-b64a-417e-87c3-25f3fc27b4fe rendered FAILED with health_check FAILED, automation execution 723, task duration 83.782s, and total workflow duration 83.809s.

Production browser validation exposed a template inheritance defect (layout/base.html did not exist). Commit 3cbbb00 corrected the timeline template to extend the canonical base.html and added regression coverage.

After deployment of 3cbbb00, the workflow execution timeline rendered successfully inside the normal HIMP navigation/layout with no internal-server error.

During Phase 14.1 deployment validation, a pre-existing daily Scheduled Updates definition caused maintenance to run during redeployment. Commit c87189b moved Scheduled Updates to the weekly Sunday 03:15 maintenance window.

Production scheduler reconciliation verified frequency=weekly, day_of_week=0, time=03:15, and next run=2026-08-23 03:15:00. The active maintenance run was allowed to finish rather than being interrupted.

A clean validation window was subsequently confirmed with himp-scheduler.service inactive and both scheduled_updates and health_check automation locks clear.

### Phase 14.1 Validation and Release Checkpoint

Branch: feature/plugin-sdk

Workflow failure propagation fix: 74feabd — fix: propagate workflow task execution failure

Weekly maintenance schedule fix: c87189b — fix: move scheduled updates to weekly maintenance window

Timeline template fix / final deployed release: 3cbbb00876e389ea990f3760c3c5949bc3fc9684 — fix: use canonical workflow timeline base template

Focused workflow/timeline regression after final template correction: 76 passed

Full isolated regression: 1063 passed

compileall: PASS

git diff --check: PASS

Production HIMP service: ACTIVE

HIMP scheduler timer: ACTIVE

Listener: 0.0.0.0:9347

Production root response after deployment: HTTP 303

LOCAL = REMOTE = DEPLOYED = 3cbbb00876e389ea990f3760c3c5949bc3fc9684

Repository/worktree: CLEAN / synchronized

Production timeline browser validation: PASS

Phase 14.1 is CLOSED. The temporary Phase 14.1 Production Validation workflow may be removed as housekeeping provided persisted execution history is retained; its validated execution history is production evidence and should not be discarded.

## 14.2 — Workflow Failure Analysis

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 14.2 extended the Phase 14.1 execution timeline with deterministic, operator-readable failure analysis derived only from persisted workflow and automation execution evidence. The implementation did not create a parallel execution or failure engine and does not infer or manufacture missing production evidence.

Failure analysis now identifies the failed workflow step and correlated automation execution, exposes persisted target information where available, surfaces direct return-code/stderr/error evidence, and analyzes composite automation results to identify failed components.

The timeline distinguishes absent evidence explicitly. When a target or error text was not persisted, the UI states that no persisted evidence is available rather than guessing.

Composite failures now show failed component name, return code, component duration, and available error evidence. The analysis also records successful components that completed before the failure and prior successful workflow-step context when such evidence exists.

The existing raw persisted failure details remain available as an expandable operator view beneath the summarized Failure Analysis card.

### Phase 14.2 Validation and Release Checkpoint

Branch: feature/plugin-sdk

Implementation commit / deployed release: e7d9b86cfacfecd51d1bea2b12388b9304f78533 — feat: add workflow failure analysis

Focused Phase 14.2 regression: 80 passed

Full isolated regression: 1067 passed

compileall: PASS

git diff --check: PASS

Production HIMP service: ACTIVE

HIMP scheduler timer: ACTIVE

LOCAL = REMOTE = DEPLOYED = e7d9b86cfacfecd51d1bea2b12388b9304f78533

Repository/worktree: CLEAN / synchronized

Production browser validation: PASS using persisted workflow execution f7236921-b64a-417e-87c3-25f3fc27b4fe and automation execution 723.

Production evidence showed failed step health_check; failed component infrastructure; return code 4; component duration 15.086s; no persisted target evidence; no persisted error text; no prior successful workflow task; and successful components docker and genericplugin before failure.

Phase 14.2 is CLOSED. No additional Phase 14.2 application changes remain.

## Remaining Phase 14 Work

Phase 14 is COMPLETE / PRODUCTION VERIFIED. Phases 14.1 through 14.5 are closed. The final Phase 14.5 production gate revalidated the complete orchestration UX, regression/build quality, PostgreSQL-backed state, scheduler/runtime behavior, release identity, rollback readiness, and test isolation safety before Phase 14 closure.

### 14.3 — Safe Retry / Replay Controls

Status: COMPLETE / PRODUCTION VERIFIED.

Add safe operator controls that clearly distinguish retrying an individual operation from rerunning an entire workflow. Inspect existing retry, confirmation, dependency, authorization, idempotency, and execution-history semantics before implementation. Resume behavior must only be exposed if the existing engine can support it safely and unambiguously; do not invent a second resume/retry engine.

### 14.4 — Workflow History & Execution Navigation

Status: COMPLETE / PRODUCTION VERIFIED.

Improve workflow-history and execution-detail navigation so operators can move cleanly among workflow definitions, workflow runs, task execution evidence, failure analysis, and related automation execution records. Reuse the existing history/detail surfaces and preserve canonical HIMP layout/navigation.

### 14.5 — Phase 14 Production Gate & Documentation

Status: COMPLETE / PRODUCTION VERIFIED. The final Phase 14 production-readiness gate passed after remediation of a test-isolation defect discovered during production validation. Full regression, compileall, diff validation, fresh remote release identity, HIMP and scheduler runtime checks, PostgreSQL-backed production validation, rollback/readiness confirmation, and production database mutation protection all passed.

### Phase 14 Remaining Sequence

1. Phase 14.5 — COMPLETE / PRODUCTION VERIFIED
2. Phase 14 — CLOSED
3. Next product phase: Phase 15 — Administration & Notifications

# Phase 14.3 - Safe Workflow Retry / Replay Controls

Status: COMPLETE / PRODUCTION VERIFIED

Phase 14.3 added bounded, auditable retry and replay controls to workflow execution history. The implementation preserves historical execution records, creates new executions for retry/replay actions, and persists explicit lineage so operators can distinguish the original execution from subsequent recovery actions.

## Implementation delivered

Added safe retry of a failed workflow step as a new standalone automation execution.

Added replay of a completed workflow execution using the current workflow definition as a new workflow execution.

Added retry lineage fields to automation executions: retry_of_execution_id and retry_source_workflow_execution_id.

Added workflow replay lineage field: replay_of_workflow_execution_id.

Extended the canonical PostgreSQL schema and repository compatibility/migration behavior for the new provenance fields.

Propagated provenance through AutomationService and WorkflowExecutionService without creating a second execution engine.

Added an admin-only Retry Failed Step action to failed timeline events.

Added an admin-only Replay Workflow action to the workflow execution timeline.

Documented the execution semantics in the UI: retry creates a standalone execution; replay runs the current workflow definition; deterministic resume remains unavailable because HIMP does not persist a workflow resume checkpoint.

Added service, repository, API, PostgreSQL-schema, provenance, and timeline UI regression coverage.

Corrected production JSON serialization for retry/replay responses by using FastAPI jsonable_encoder.

## Commits and release state

4093501 - feat: add safe workflow retry and replay controls

7ac3ac0 - fix: serialize workflow retry replay responses

Final deployed revision: 7ac3ac01e7c8543265efb1b3ba4a94d2b8e44db5

LOCAL = REMOTE = DEPLOYED at final verification.

Repository state: feature/plugin-sdk synchronized with origin and clean.

## Regression and build validation

Expanded Phase 14.3 focused regression: 191 passed.

Serialization-focused regression after the production fix: 47 passed.

Final full isolated regression: 1082 passed in 5.01 seconds.

Python compile validation: PASS.

git diff --check: PASS.

## Production retry validation

The original failed health_check automation execution was execution 723 and remained historical and unchanged. A production retry created a new successful standalone automation execution. Post-fix validation of execution 725 confirmed success=1, retry_of_execution_id=723, retry_source_workflow_execution_id=f7236921-b64a-417e-87c3-25f3fc27b4fe, and workflow_execution_id=NULL. The health_check automation lock was released after execution.

## Production replay validation

The original failed workflow execution f7236921-b64a-417e-87c3-25f3fc27b4fe remained FAILED. Replay created the distinct workflow execution f3e0be11-65c5-4f69-ad21-0fd09e154807. The replay completed successfully and persisted replay_of_workflow_execution_id=f7236921-b64a-417e-87c3-25f3fc27b4fe. Its health_check automation execution was execution 726, success=1, and was associated with the new replay workflow execution.

## Production platform validation

HIMP service active after deployment.

HIMP scheduler timer active after deployment.

Port 9347 listening under Uvicorn.

Unauthenticated root HTTP check returned 303 as expected.

Retry and replay controls visually verified in the production workflow execution timeline.

PostgreSQL lineage columns verified present in automation_executions and workflow_executions.

REPLAY_PROVENANCE=PASS.

## Phase 14.3 closure decision

Phase 14.3 is closed as COMPLETE / PRODUCTION VERIFIED. The retry and replay recovery paths are now bounded, provenance-preserving, admin-controlled, regression-covered, deployed, and live validated.

## Next Phase

Proceed to the next Phase 14 roadmap slice defined by this authoritative roadmap. Before implementation, confirm the exact Phase 14.4 scope from the roadmap and retain the established one-slice-at-a-time workflow: implement end-to-end, consolidate testing at the end of the slice, production-validate, then update this authoritative roadmap.

# Phase 14.4 - Workflow History & Execution Navigation

Status: COMPLETE / PRODUCTION VERIFIED

Phase 14.4 completed the operator navigation layer around persisted workflow and automation execution history while preserving the existing HIMP workflow and AutomationService execution architecture.

## Implementation delivered

Added an authenticated Workflows landing page and canonical sidebar entry.

Added per-workflow persisted history navigation with direct links to individual workflow execution timelines.

Changed workflow timeline return navigation to the workflow-specific history surface rather than global history.

Exposed workflow replay lineage in history and timeline views.

Added automation execution provenance navigation derived from persisted workflow_execution_id, retry_source_workflow_execution_id, and retry_of_execution_id evidence.

Added an Execution Provenance card to automation execution details so operators can return to originating or retry-source workflow runs when persisted lineage exists.

Corrected Workflow History back-navigation to return to the Workflows landing page.

Preserved canonical base.html/sidebar layout and existing execution/history services rather than creating parallel navigation or persistence subsystems.

## Commits and release state

ad3faf7 — feat: add workflow history navigation

876ce78 — fix: expose workflow navigation in operator ui

708c867 — fix: preserve scheduler timer state during deploy

4872f51 — fix: return workflow history to workflows

Final deployed revision: 4872f51e961b5eb3bfe0546d954975fda610b754

LOCAL = REMOTE = DEPLOYED at final verification.

Repository state: feature/plugin-sdk synchronized with origin and clean.

## Regression and build validation

Focused Phase 14.4 navigation regression: 72 passed.

Focused scheduler deployment lifecycle regression: 19 passed.

Final full regression after scheduler deployment hardening: 1102 passed.

Python compile validation: PASS.

git diff --check: PASS.

## Production browser and runtime validation

Workflows sidebar navigation and landing page visually verified in production.

Workflow History and View Run navigation visually verified against persisted workflow executions.

Workflow execution timeline and replay lineage navigation visually verified.

Automation execution provenance navigation visually verified using persisted execution lineage.

Normal deployment now installs/enables the scheduler timer but leaves its runtime state unchanged unless HIMP_START_SCHEDULER_TIMER=1 is explicitly supplied.

Deployment verification proved the scheduler timer InvocationID and ActiveEnterTimestamp were unchanged across deployment.

A live scheduled_updates run completed successfully at 2026-08-22 14:59 EDT; the schedule last_run advanced to 2026-08-22 18:59:00 UTC, due_now became false, and due task IDs became empty.

After explicitly restarting the scheduler timer, consecutive scheduler evaluations reported Due tasks: 0, Due remediation schedules: 0, and No scheduled work is due.

Final scheduler service state: inactive/dead between timer ticks with Result=success and ExecMainStatus=0.

Final scheduler timer state: active/waiting and enabled.

Final systemd failed-unit count: 0.

## Phase 14.4 closure decision

Phase 14.4 is closed as COMPLETE / PRODUCTION VERIFIED. Workflow definitions, persisted workflow runs, task execution evidence, replay/retry lineage, and automation execution provenance are now connected through the canonical operator UI. Scheduler deployment lifecycle behavior was also hardened and live-validated without changing scheduler execution semantics.

## Next Phase

Phase 14.5 is COMPLETE / PRODUCTION VERIFIED and Phase 14 is CLOSED. Proceed to Phase 15 — Administration & Notifications from release fdf66a5d774790809494a076cdac53ba81478b00 with the final Phase 14 regression baseline of 1108 passing tests and the permanent pytest production-database isolation guard in place.

# Phase 14.5 - Phase 14 Production Gate & Documentation

Status: COMPLETE / PRODUCTION VERIFIED

Phase 14.5 closed Phase 14 through a production-readiness gate rather than a new feature slice. The gate revalidated release identity, HIMP runtime health, scheduler state, PostgreSQL persistence behavior, regression/build quality, rollback assets, deployment safety, and operator-facing workflow/orchestration UX.

## Final production-gate findings and remediations

The initial Phase 14.5 gate passed focused regression (77 passed), full regression (1102 passed), compileall, diff validation, HIMP runtime checks, rollback/runbook checks, and deployment scheduler-safety checks, but exposed unexpected scheduler due-state regression in production.

Root cause: pytest was launched from an operator shell that still had /etc/himp/database.env exported. With no root pytest isolation configuration, tests/test_scheduler_repository.py instantiated SchedulerRepository against live PostgreSQL and wrote fixture last_run values into the production automation_schedules table.

The scheduler itself was not defective. Successful scheduled_updates acknowledgement had correctly advanced last_run to 2026-08-22 18:59:00 UTC and due_now=False before pytest later overwrote the value with a historical fixture timestamp.

Production scheduler state was repaired using the preserved acknowledgement updated_at values for health_check and scheduled_updates. Post-repair due_tasks became empty and both tasks reported due=False.

A root conftest.py test safety boundary was added. Before test modules import, pytest now forces HIMP_DATABASE_BACKEND=sqlite, uses a process-local disposable SQLite file, and removes inherited PostgreSQL connection variables from the pytest process. Tests that intentionally exercise PostgreSQL configuration may still override synthetic values locally.

Exact regression proof: the scheduler repository tests that had previously contaminated production ran with the parent shell still configured for production PostgreSQL; 9 tests passed, the temporary SQLite database was cleaned up, and production before/after snapshots were identical (PRODUCTION_DATABASE_MUTATED=NO).

Full-suite proof: 1107 tests passed with production PostgreSQL variables still exported in the parent shell; the process-local pytest database was cleaned up and the complete production automation_schedules snapshot was unchanged (FULL_SUITE_PRODUCTION_DATABASE_MUTATED=NO).

A deployment edge case was then found: systemctl status himp-scheduler.timer returned nonzero while the timer was intentionally inactive, causing the systemd installer to abort under set -e. The informational status command was made nonfatal with || true and covered by regression tests.

Final full regression after the inactive-timer installer fix: 1108 passed. compileall: PASS. git diff --check: PASS.

## Commits and release state

26ecc41 — fix: isolate pytest from production database

fdf66a5 — fix: allow inactive scheduler during systemd install

Final application release: fdf66a5d774790809494a076cdac53ba81478b00

Fresh GitHub fetch verification succeeded over SSH port 443 after verifying ssh.github.com Ed25519 fingerprint SHA256:+DiY3wvvV6TuJJhbpZisF/zLDA0zPMSvHdkr4UvCOqU.

Final identity: LOCAL = REMOTE = DEPLOYED = fdf66a5d774790809494a076cdac53ba81478b00.

Repository status at gate completion: feature/plugin-sdk synchronized with origin; only this roadmap document remained untracked pending documentation closure.

## Final production validation

HIMP service: active/running with Result=success and ExecMainStatus=0.

Uvicorn listener: 0.0.0.0:9347.

Scheduler timer: active/waiting and enabled; runtime state preserved by normal deployment unless explicitly started with HIMP_START_SCHEDULER_TIMER=1.

Scheduler service between timer ticks: inactive/dead with Result=success and ExecMainStatus=0.

Production due_tasks=[] at final gate.

health_check last_run=2026-08-22 18:34:30.115882 UTC; due_now=False.

scheduled_updates last_run=2026-08-22 18:59:00.792123 UTC; due_now=False.

Final systemd failed-unit count: 0.

Deployment with scheduler timer intentionally inactive completed successfully, updated .himp-release, and did not start/restart the timer. The timer was explicitly started afterward and returned to active/waiting.

Rollback/readiness runbook present and validated: docs/operations/HIMP_RELEASE_UPGRADE_ROLLBACK.md.

Full regression baseline: 1108 passed.

FULL_SUITE_PRODUCTION_DATABASE_MUTATED=NO.

SCHEDULER_DEPLOY_SAFETY=PASS.

## Phase 14 closure decision

Phase 14 — Workflow & Orchestration UX is CLOSED as COMPLETE / PRODUCTION VERIFIED. The final production gate validated workflow history/navigation, execution timelines, failure analysis, safe retry/replay provenance, PostgreSQL-backed scheduler state, release/rollback readiness, deployment timer safety, and a permanent pytest isolation boundary that prevents ordinary regression runs from inheriting production database credentials.

## Next Phase

Proceed to Phase 15 — Administration & Notifications. Start by confirming the exact Phase 15 scope in this authoritative roadmap, then continue the established one-slice-at-a-time workflow: inspect, implement end-to-end, consolidate testing at the end of the slice, production-validate, and update this roadmap at closure.

# 7. Phase 15 — Administration & Notifications

Introduce a reusable notification framework that routes operational events without coupling individual monitoring features to specific transports.

Notification event model and routing policy.

Discord incoming webhooks are the approved initial outbound transport. Additional transports require explicit security and operational justification.

Severity, suppression, acknowledgement, escalation, and recovery semantics.

Storage events explicitly supported: STORAGE_WARNING, STORAGE_CRITICAL, STORAGE_RECOVERED.

Health, automation, remediation, backup, and other operational event sources can later reuse the same framework.

Administrative notification management UI, authorization, acknowledgement, delivery audit history, protected secret handling, and production gate.

## Phase 15.1 — Notification Framework

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 15.1 established the reusable, transport-independent notification foundation for HIMP. The implementation added a durable notification event model, PostgreSQL-backed notification repository, routing and lifecycle service, and storage-capacity integration without coupling storage monitoring to any email/chat transport.

Implementation commit: b68e1b30d8b5f884abb793b07305faa4d773b1b6 — feat: add notification framework.

Canonical PostgreSQL schema increased from 24 to 25 HIMP tables with the new notifications table.

Notification lifecycle semantics include PENDING, ACKNOWLEDGED, SUPPRESSED, and RECOVERED states with routing decisions, logical destinations, deduplication keys, correlation keys, acknowledgement evidence, recovery evidence, and metadata persistence.

Storage notification sources now support STORAGE_WARNING, STORAGE_CRITICAL, and STORAGE_RECOVERED transitions through the shared notification service.

Duplicate active notifications are persisted as SUPPRESSED with suppression_reason='duplicate active notification' rather than repeatedly routed.

The production PostgreSQL smoke test proved warning routing, duplicate suppression, acknowledgement, recovery correlation, and cleanup end-to-end.

Production smoke-test synthetic records: 3 created, lifecycle validated, 3 deleted, 0 synthetic rows remaining.

Production notifications table: public.notifications present with 20 expected columns; final row count after synthetic cleanup: 0.

Focused Phase 15.1 regression: 27 passed. Final full regression: 1125 passed. compileall: PASS. git diff --check: PASS.

Final release identity: LOCAL = REMOTE = DEPLOYED = b68e1b30d8b5f884abb793b07305faa4d773b1b6.

Production HIMP service: active/running on 0.0.0.0:9347. Scheduler timer restored to active/waiting; scheduler service inactive/dead with Result=success between ticks; failed units: 0; repository/worktree: clean and synchronized.

Production validation also exposed a deployment-readiness race: systemd can report himp.service active before application initialization has completed. This did not invalidate Phase 15.1; the notifications table appeared correctly once HIMP initialization completed. Application-level readiness should be hardened in a later bounded deployment/reliability slice rather than expanding the completed notification-framework slice.

## Phase 15.2 — Configurable Notification Destinations

Status: COMPLETE / PRODUCTION VERIFIED (Discord delivery slice). External generic webhooks and RSS/Atom are intentionally out of current scope.

Phase 15.2 delivered the first production notification transport: Discord incoming webhooks. The implementation preserves the transport-independent Phase 15.1 event/lifecycle model, records delivery outcomes separately, protects webhook secrets outside the database, and has been live validated end-to-end in production.

Implementation commit: 5726a5d6c8e3763a4bd1b596fd095ea64f27a064 — feat: add discord notification delivery.

Added notification_deliveries persistence and PostgreSQL schema support so transport attempts are audited separately from the operational notification lifecycle.

Added a notification delivery service and transport abstraction with Discord incoming-webhook support while keeping Discord-specific logic out of event producers.

Added protected notification configuration installation. Production secret file /etc/himp/notifications.env is root:root with mode 0600; the webhook URL is loaded into the HIMP service environment without being displayed in validation output.

Production deployment created public.notification_deliveries with the expected delivery-audit columns. Initial production row count was 0.

Live Discord smoke test created a synthetic STORAGE_CRITICAL notification, routed it to logical destination DEFAULT, delivered it successfully to Discord, and recorded status=SUCCESS with HTTP status_code=204.

The synthetic smoke-test delivery and notification rows were deleted after validation; remaining synthetic notifications=0, remaining synthetic deliveries=0, and final production counts returned to notifications=0 and notification_deliveries=0.

Focused Discord regression: 32 passed. Implementation full regression: 1135 passed. compileall: PASS. git diff --check: PASS.

Final production release identity: LOCAL = REMOTE = DEPLOYED = 5726a5d6c8e3763a4bd1b596fd095ea64f27a064.

Production HIMP service is active/running and listening on 0.0.0.0:9347. The scheduler timer was restored to active/waiting only after a due-work check returned no due tasks; the first evaluation completed with Due tasks: 0 and Due remediation schedules: 0; failed units: 0.

Repository/worktree is clean and synchronized. Product direction after production validation was narrowed for security: do not build generic external outbound webhooks, and defer RSS/Atom indefinitely unless a future operational need justifies revisiting it.

## Phase 15.3 — Notification Management UX

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 15.3 added the authenticated operator-facing notification management surface over the existing Phase 15.1 lifecycle and Phase 15.2 delivery-audit contracts. It did not create a parallel notification subsystem.

Implementation commit: ef494ad530e69f8a13b96a0d96c56d4592f450d9 — feat: add notification management ux.

Added the Notifications sidebar surface with summary cards for visible notifications, pending notifications, critical notifications, and delivery failures.

Added lifecycle-status and severity filtering over persisted notifications.

Notification history exposes severity, event, source, message, lifecycle state, delivery state, occurrence time, acknowledgement evidence, and bounded actions.

Authenticated administrators can acknowledge pending notifications from the UI. Acknowledgement persists the administrator identity and timestamp, changes lifecycle state to ACKNOWLEDGED, and removes the redundant acknowledgement action.

Production authorization proof: unauthenticated GET /notifications returned HTTP 303 to the authentication flow rather than exposing notification data publicly.

Production live UX proof used one synthetic STORAGE_CRITICAL event. HIMP displayed 1 visible / 1 pending / 1 critical / 0 delivery failures; Discord delivery showed SUCCESS / HTTP 204; PENDING + CRITICAL filtering worked; browser acknowledgement changed pending from 1 to 0 and persisted acknowledged_by=admin with acknowledged_at evidence.

Post-acknowledgement PostgreSQL verification confirmed lifecycle_status=ACKNOWLEDGED and Discord delivery status=SUCCESS with HTTP 204.

Synthetic Phase 15.3 records were removed after validation; the remaining synthetic notification count was 0.

Focused Phase 15.3 regression: 30 passed. Final full regression: 1147 passed. compileall: PASS. git diff --check: PASS.

Final Phase 15.3 application identity: LOCAL = REMOTE = DEPLOYED = ef494ad530e69f8a13b96a0d96c56d4592f450d9.

Final runtime: HIMP active/running; scheduler safety check due_tasks=[]; scheduler timer restored to active/waiting; scheduler service inactive/dead between ticks with Result=success; failed units=0; repository clean and synchronized.

## Phase 15 Notification Strategy Decisions and Future Capabilities

Security is the governing design constraint. Notification expansion must not weaken homelab security merely to add integrations.

Discord remains the approved production notification destination for the current Phase 15 implementation.

Do not implement generic external outbound webhooks in the current roadmap. The previously considered generic HTTPS JSON webhook transport is explicitly tabled because it expands outbound integration and secret-management surface without a demonstrated need.

Do not implement RSS/Atom now. RSS was considered as a lightweight read-only feed but is removed from the active Phase 15 plan and may only be reconsidered later if a concrete use case appears.

Home Assistant integration is a future capability, not current Phase 15 scope. Do not build it until Home Assistant has been migrated from the current Odroid deployment to a VM.

When Home Assistant integration is revisited, prefer a tightly scoped internal-only design with least privilege, explicit authentication, bounded event types, no unnecessary Internet exposure, and no generic externally callable webhook surface.

Potential Home Assistant uses include presenting HIMP health/notification state in dashboards and using selected HIMP events for local automations, but the exact contract must be designed after the VM migration and a fresh security review.

Email, Microsoft Teams, Slack, bot accounts, broad notification rules engines, and additional transports remain out of scope unless future production evidence creates a clear requirement.

A later bounded deployment/reliability slice should address the previously observed readiness race where systemd may report himp.service active before application initialization is complete. This remains separate from notification semantics.

Operator-facing timestamp formatting may be polished later (for example, removing raw microseconds and using a human-readable local display). This is UX polish, not a Phase 15.3 correctness blocker.

## Phase 15.4 — Phase 15 Production Gate & Documentation

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 15.4 closed Phase 15 through a verification-only production-readiness gate. No new notification behavior was added. The gate revalidated the complete notification framework, Discord delivery path, notification management UX, authentication boundary, secret handling, scheduler state, regression quality, release/rollback assets, and clean repository state.

## Final Phase 15 production-gate evidence

Focused Phase 15 regression: 39 passed.

Full regression: 1147 passed in 5.19 seconds.

compileall: PASS. git diff --check: PASS.

Repository identity: LOCAL = REMOTE = 575b34fc3d38ba13f48fc4e624a0010aca9291c6.

Deployed application release: ef494ad530e69f8a13b96a0d96c56d4592f450d9. The LOCAL/REMOTE versus DEPLOYED difference is intentional because 575b34f is documentation-only.

HIMP runtime: active/running with Result=success and ExecMainStatus=0; Uvicorn listening on 0.0.0.0:9347.

Authentication boundary: root application request returned HTTP 303 and an unauthenticated /notifications request returned HTTP 303.

Discord secret safety: /etc/himp/notifications.env remained root:root mode 0600 and HIMP_DISCORD_WEBHOOK_URL was confirmed loaded without exposing the secret.

Production notification state at closure: notifications total=0, pending=0; notification_deliveries contained no production rows.

Scheduler safety: due_tasks=[]; himp-scheduler.timer active/waiting; himp-scheduler.service inactive/dead between ticks with Result=success and ExecMainStatus=0.

Failed systemd units: 0.

Release/readiness assets: scripts/deploy/himp.sh PASS; docs/operations/HIMP_RELEASE_UPGRADE_ROLLBACK.md PASS; authoritative roadmap present.

Repository/worktree: clean and synchronized.

## Phase 15 closure decision

Phase 15 — Administration & Notifications is CLOSED as COMPLETE / PRODUCTION VERIFIED. The phase delivered a reusable transport-independent notification model, PostgreSQL-backed lifecycle persistence, storage warning/critical/recovery events, duplicate suppression, acknowledgement and recovery semantics, Discord delivery with separate delivery auditing, protected secret handling, and an authenticated operator notification-management surface.

No Phase 15.5 feature slice is required. Discord remains the approved production transport. Generic external webhooks and RSS/Atom remain tabled. Home Assistant remains a future internal-only integration candidate after the planned migration from the Odroid deployment to a VM and a fresh security review.

Deferred polish remains non-blocking: human-readable operator timestamp formatting and a bounded application-readiness/deployment reliability improvement for the previously observed systemd-active-before-initialization race.

# 8. Phase 16 — Platform Lifecycle & Advanced Operations

Reserve Phase 16 for product lifecycle capabilities justified by real operational needs after Phases 12–15. Candidate work includes richer maintenance-window controls, lifecycle visibility, advanced operational reporting, capacity forecasting after sufficient history exists, and other cross-platform operational improvements. Scope should be approved from production evidence rather than implemented merely because it appears on the roadmap.

# 9. Immediate Starting Point

Phase 16 is ACTIVE. Phase 16.1 HTTPS/Web Transport Hardening, Phase 16.3 secure-host-onboarding and vulnerability-intelligence integration, Phase 16.4 inventory-driven Greenbone onboarding, Phase 16.5 vulnerability-operations UX, Phase 16.6 vulnerability historical comparison and PDF/TXT/CSV reporting, Phase 16.7 bounded ad-hoc vulnerability scanning, Phase 16.8.1 Application Operations Overview, and Phase 16.8.2 Operational Attention Overview are COMPLETE / PRODUCTION VERIFIED. Phase 16.8.2 extended the canonical /application-health Application Operations surface with a read-only, dynamic Operational Attention view sourced from the existing Dashboard operational summary contract.

# 10. Roadmap Decision Record

2026-08-22 Phase 15 closure checkpoint: Phase 15.1 notification framework, Phase 15.2 Discord delivery, Phase 15.3 notification management UX, and Phase 15.4 production gate are COMPLETE / PRODUCTION VERIFIED. Final Phase 15 full regression baseline is 1147 passing tests. The verified application release is ef494ad530e69f8a13b96a0d96c56d4592f450d9. The final Phase 15 closure documentation commit is 62f41839b1de50e5c29a5b23f433e11e1c2ef256. Production notification and delivery tables contained zero operational rows at closure, scheduler due_tasks=[], failed units=0, and all release/readiness assets passed. Phase 16 is now the active roadmap phase.

This roadmap intentionally does not reopen completed Phase 9–13 foundation work. Phase 12 Operational Intelligence remains COMPLETE / PRODUCTION VERIFIED. Phase 13 Automation Intelligence is now COMPLETE / PRODUCTION VERIFIED: 13.1 added deterministic evidence-backed recommendations; 13.2 added a durable approval queue; 13.3 added controlled one-time scheduling; 13.4 separated execution success from condition-aware verification; 13.5 added a bounded fail-closed autonomous-remediation framework with an empty production allowlist; and 13.6 revalidated the entire Phase 13 production surface. The final application release checkpoint for Phase 13 is 4282dab4a497deee4eb86b53ed732cc72498c3cb with a 1050-test full regression baseline. The synchronized repository checkpoint after Phase 13.5 closure documentation is 60ad66f633a9c8d0ae76c0c2ae889f6f061e627d; the difference is documentation-only. Phase 13.6 found no HIMP runtime, scheduler, PostgreSQL, remediation-safety, or regression defects. Historical systemd failed-state residue was classified and cleared, leaving zero failed units. Phase 14 — Workflow & Orchestration UX is the next development phase. Predictive/AI behavior remains deferred. Phase 14.1 is now COMPLETE / PRODUCTION VERIFIED. It added persisted workflow execution timeline visibility, correlated automation task evidence, step timing/status, and failure presentation while reusing the existing AutomationService execution framework. Production validation found and corrected nested automation-result failure propagation (74feabd), moved Scheduled Updates to the weekly Sunday 03:15 maintenance window (c87189b), and corrected the timeline template to use the canonical base.html (3cbbb00). The final Phase 14.1 baseline is 1063 passing tests with LOCAL = REMOTE = DEPLOYED = 3cbbb00876e389ea990f3760c3c5949bc3fc9684. Phase 14.2 is now COMPLETE / PRODUCTION VERIFIED. Commit e7d9b86 added deterministic workflow failure analysis using persisted execution evidence, including failed-step context, component failures, return-code/error evidence where available, prior successful-step context, and successful components before failure. The final Phase 14.2 baseline is 1067 passing tests with LOCAL = REMOTE = DEPLOYED = e7d9b86cfacfecd51d1bea2b12388b9304f78533. Production browser validation against workflow execution f7236921-b64a-417e-87c3-25f3fc27b4fe confirmed failed component infrastructure with return code 4 while correctly reporting that target and error text were not persisted. Remaining Phase 14 work is 14.3 Safe Retry / Replay Controls, 14.4 Workflow History & Execution Navigation, and 14.5 Phase 14 Production Gate & Documentation. Phase 14.3 is COMPLETE / PRODUCTION VERIFIED with bounded retry/replay controls and persisted provenance. Phase 14.4 is COMPLETE / PRODUCTION VERIFIED with workflow landing/history navigation, execution timeline navigation, replay lineage, automation execution provenance, and canonical sidebar integration. The Phase 14.4 production checkpoint was 4872f51e961b5eb3bfe0546d954975fda610b754 with 1102 passing tests. Phase 14.5 is now COMPLETE / PRODUCTION VERIFIED and Phase 14 — Workflow & Orchestration UX is CLOSED. During the final gate, running pytest from an operator shell with production PostgreSQL environment variables was proven capable of mutating live scheduler state through repository tests. Production scheduler acknowledgement state was repaired, a root conftest.py now forces pytest onto a process-local disposable SQLite database before test-module import, and an exact before/after production snapshot proved the full 1107-test suite made zero scheduler-table changes. A follow-up installer fix made inactive scheduler timer status reporting nonfatal; the final regression baseline increased to 1108 passing tests. Deployment with the timer intentionally inactive completed successfully, preserved timer runtime state, and updated the release marker. The timer was then explicitly restarted and settled active/waiting with the scheduler service inactive/dead and zero failed units. Fresh GitHub verification over SSH port 443 succeeded after host-key fingerprint verification. Final Phase 14 release identity is LOCAL = REMOTE = DEPLOYED = fdf66a5d774790809494a076cdac53ba81478b00. The next product phase is Phase 15 — Administration & Notifications. Predictive/AI behavior remains deferred. Phase 15.1 is now COMPLETE / PRODUCTION VERIFIED. Commit b68e1b30d8b5f884abb793b07305faa4d773b1b6 established the reusable notification event, persistence, routing, suppression, acknowledgement, escalation/recovery foundation and integrated storage-capacity transitions. The final Phase 15.1 baseline is 1125 passing tests with LOCAL = REMOTE = DEPLOYED at b68e1b30d8b5f884abb793b07305faa4d773b1b6. Production PostgreSQL lifecycle validation passed and all synthetic smoke-test notification rows were removed. Phase 15.2 — Configurable Notification Destinations is the next bounded product slice. At the initial Phase 15.2 planning checkpoint, Discord, generic outbound HTTPS webhooks, and RSS/Atom were considered. That planning position was later superseded by the Phase 15 security decision: Discord is the approved production transport; generic external webhooks are out of scope; RSS/Atom is tabled; and Home Assistant remains a future internal-only integration after its VM migration and a fresh security review. Email, Teams, Slack, bot accounts, and a broad notification rules engine are not required for the initial Phase 15.2 slice unless later production evidence justifies them. Phase 15.2 Discord delivery is now COMPLETE / PRODUCTION VERIFIED at release 5726a5d6c8e3763a4bd1b596fd095ea64f27a064. The production smoke test delivered a synthetic STORAGE_CRITICAL event to Discord with HTTP 204 and SUCCESS delivery audit, then removed all synthetic records. The notification secret remains outside PostgreSQL in /etc/himp/notifications.env with root:root 0600 protection. The scheduler was restored only after confirming no due production work; its first evaluation completed with zero due tasks and zero failed units. That earlier transport-expansion plan is superseded. No additional Phase 15 transport is planned: generic external webhooks are out of scope, RSS/Atom is tabled, and Home Assistant integration is deferred until the Odroid-to-VM migration is complete and an internal-only security-reviewed design is approved.

# Phase 16.1 Closure Addendum — HTTPS, Web Transport Hardening, and Vulnerability Validation

Status: COMPLETE / PRODUCTION VERIFIED

Phase 16.1 was selected from production security evidence as the first bounded Phase 16 lifecycle/operations slice. The work removed direct LAN exposure of HIMP's Uvicorn application listener, introduced an internal HTTPS reverse-proxy boundary, made the firewall/TLS deployment reproducible, corrected the deployment readiness race identified during Phase 15 closure, and validated the resulting production surface with a dedicated Greenbone Community Edition vulnerability-scanner VM.

## Production HIMP Transport Architecture

Canonical HIMP name: automation.server.arpa

HIMP address: 10.10.37.56

External application transport: HTTPS on TCP 443 through Caddy.

HTTP on TCP 80 is retained only for LAN-scoped HTTP-to-HTTPS redirection.

Uvicorn is bound to 127.0.0.1:9347 and is no longer directly reachable from the LAN.

Uvicorn accepts proxy headers only from 127.0.0.1.

nftables permits TCP 80/443 only from 192.168.37.0/24, 192.168.10.0/24, and 10.10.37.0/24, then drops other TCP 80/443 traffic and drops TCP 9347.

Caddy terminates TLS using the internal mkcert-issued certificate for automation.server.arpa, automation, and 10.10.37.56.

Observed certificate validity: 2026-08-23 through 2028-11-23.

Security headers include Strict-Transport-Security: max-age=31536000, X-Content-Type-Options: nosniff, X-Frame-Options: DENY, Referrer-Policy: strict-origin-when-cross-origin, and a restrictive Permissions-Policy.

## Git-Managed Phase 16.1 Assets

caddy/Caddyfile — internal HTTPS reverse proxy and response-header policy.

config/firewall/nftables.conf — reproducible LAN-only TCP 80/443 boundary and TCP 9347 denial.

scripts/tls/install.sh — idempotent Caddy/TLS/firewall installation and validation.

systemd/himp.service — Uvicorn loopback binding plus trusted proxy-header handling.

scripts/deploy/himp.sh — application-readiness gate before release-marker completion.

tests/deployment/test_himp_deployment.py — deployment-readiness regression coverage.

## Implementation and Release Checkpoints

8c85625234884d814d6b7e2270a736dc4ea66b1e — feat: harden HIMP web transport with HTTPS.

63ad77b60d507d2fb61b3d322ca58d72bd65149b — feat: finalize HIMP transport hardening.

b67aee672d01ad727cc2fb840f9be3e1b0539f69 — fix: wait for HIMP application readiness on deploy.

Final repository/application identity: LOCAL = REMOTE = DEPLOYED = b67aee672d01ad727cc2fb840f9be3e1b0539f69.

Final worktree state: clean and synchronized.

## Deployment Readiness Correction

Production alignment briefly produced an HTTP 502 immediately after systemd reported himp.service active. Diagnosis confirmed that systemd service activation could precede completion of FastAPI/Uvicorn application initialization. The deployment contract was therefore strengthened to wait first for the systemd service and then for a successful application-level HTTP readiness response from 127.0.0.1:9347 before writing /opt/himp/.himp-release and declaring deployment complete.

Focused deployment regression after the correction: 30 passed.

New readiness-specific tests: 2 passed.

Final full regression: 1149 passed in 5.39 seconds.

compile/static/diff validation: PASS.

Live deployment proof emitted 'HIMP application is ready.' before release completion.

Immediate post-deployment loopback response: HTTP 303; HTTPS /login response: HTTP 200.

Failed systemd units: 0.

## Dedicated Vulnerability Scanner — New Server

| Item | Validated State |
| --- | --- |
| Hostname / FQDN | vulnscanner.server.arpa |
| Address | 10.10.37.62/24 |
| Operating system | Debian GNU/Linux 12 (bookworm); Debian 12.15 observed |
| Kernel | 6.1.0-52-amd64 |
| Virtualization | KVM / QEMU |
| CPU | 4 vCPU |
| Memory | 7.8 GiB RAM |
| Swap | None |
| Root storage | /dev/sda1 ext4; approximately 99 GiB usable after expansion to 100 GiB |
| Observed post-Greenbone storage | 43 GiB used / 52 GiB available / 46% utilization |
| Default gateway | 10.10.37.1 |
| DNS | 10.10.37.9 and 192.168.10.70; search domain server.arpa |
| QEMU guest agent | Active |
| Greenbone installation | /opt/greenbone |
| Greenbone management exposure | Local-only; web interface bound to 127.0.0.1 and administered through SSH tunneling |
| Firewall posture | Restrictive nftables policy; scanner forwarding narrowly authorized for HIMP |
| Failed systemd units at build checkpoint | 0 |

## Greenbone Deployment and Baseline

Greenbone Community Edition deployed from the current official Compose definition in /opt/greenbone/compose.yaml.

Core stack includes gvmd, GSA/GSAD/nginx, ospd-openvas, openvas/openvasd, PostgreSQL, Redis, Notus, SCAP, CERT, report-format, and vulnerability-test data services.

GVMD version observed during deployment: 26.36.1; Manager DB revision 281.

Initial VT, CERT, and SCAP imports completed successfully. The SCAP database initialization was verified as active processing rather than a deadlock.

The Greenbone management interface remains intentionally unavailable directly from the LAN.

Docker bridge forwarding was repaired and persisted without broadening Greenbone management exposure.

A real reboot validated nftables persistence, Docker bridge recreation, Greenbone frontend availability, and zero failed systemd units.

## Greenbone HIMP Scan Evidence

Controlled target: HIMP at 10.10.37.56.

Original unauthenticated baseline report UUID: eb9cc9eb-2e01-4a37-8c51-82e0ea5132fe; completed at 100% with 24 results.

Post-hardening intermediate report UUID: d1d1b35c-438f-44f4-bb4c-9a52b8c9a1ac; completed at 100% with 66 results.

Final closure report UUID: 1fec5764-c0d4-45ed-9ebc-d67c375ca49e.

Final closure scan: 100% complete; 66 results; started 2026-08-23 14:24:28 UTC; ended 2026-08-23 15:20:58 UTC.

Final scored summary observed before completion: 0 critical, 0 high, 2 medium, 4 low, 57 informational; maximum severity 5.9.

TCP 9347 results in final scan: 0.

Non-informational TCP 443 findings: 0.

The HSTS-related header-search result was severity 0 informational; direct production validation confirmed Strict-Transport-Security: max-age=31536000.

## Residual Findings and Scope Decision

The remaining scored findings are not web-transport defects and do not reopen Phase 16.1. They are retained as separate host-hardening evidence for later Phase 16 prioritization.

SSH/22: ChaCha20-related scanner finding, severity 5.9, QOD 30.

SSH/22: OpenSSH version-related finding, severity 5.3, QOD 50.

SSH/22: weak UMAC-64 MAC algorithms, severity 2.6, QOD 80.

General TCP: RFC1323/RFC7323 timestamp observation, severity 2.6, QOD 80.

SSH/22: version-related finding referencing fixed version 10.1, severity 2.4, QOD 30.

General ICMP: ICMP timestamp reply observation, severity 2.1, QOD 80.

## Phase 16.1 Closure Decision

Phase 16.1 — HIMP HTTPS & Web Transport Hardening is CLOSED as COMPLETE / PRODUCTION VERIFIED. HIMP now uses a reproducible, internal-only HTTPS boundary; direct TCP 9347 LAN access is removed; the deployment process waits for application readiness; and a completed Greenbone scan independently verified zero results on TCP 9347 and zero non-informational findings on TCP 443.

## Immediate Next Starting Point

Begin the next bounded Phase 16 slice from production evidence. Review the residual SSH/TCP/ICMP findings as candidates for host hardening, without reopening the completed HTTPS transport slice. Continue to keep integrations internal-only by default and preserve the existing security-first roadmap decisions.

## Phase 16.3 - Simplified Secure Host Onboarding

Status: COMPLETE / PRODUCTION VERIFIED

Phase 16.3 converted the production SSH/Ansible onboarding lessons into a deterministic operator workflow while preserving support for older hosts that already have a usable administrative or Ansible account. The implementation keeps the actual HIMP runtime identity explicit: HIMP performs managed SSH as the himp service account with /var/lib/himp/.ssh/id_ed25519.

### Delivered Operator UX

The Add Host workflow now includes an SSH Setup action and guidance for both supported onboarding paths.

Existing / legacy account path: older hosts may retain an existing administrative or Ansible account such as root, lou, or another approved account. HIMP installs its public key for that account, verifies SSH as the actual himp service identity, verifies passwordless sudo when Become is enabled, and finishes with an Ansible validation command.

Dedicated HIMP automation account path: new Linux hosts are guided toward himp-automation with password locked, public-key authentication, a dedicated authorized_keys file, validated sudoers policy, Ansible User = himp-automation, and Become enabled.

The UI explicitly distinguishes the HIMP service SSH key from root or operator SSH keys and uses /var/lib/himp/.ssh/id_ed25519 for validation.

Host-key enrollment uses StrictHostKeyChecking=accept-new so first connection can be enrolled without disabling host-key checking.

The onboarding modal provides copy/paste-safe commands for key transfer, SSH verification, sudo verification, and final Ansible validation.

### Inventory Group Selector Regression and Correction

Production browser validation exposed a regression in the Add Host Group selector after the Phase 16.3 JavaScript replacement. The selector no longer populated the live inventory groups.

Commit 7cbce8faefba8b5804905eb720458a30b729649e restored the original HIMP Inventory Group Selector behavior, including GET /api/inventory/groups, Add Host and Edit Host modal refresh handling, group counts, and the Select a group placeholder.

Regression coverage was extended so future Phase 16.3 UX changes must preserve the inventory group loader contract.

Final browser validation confirmed the production Add Host Group selector populated the current inventory groups and host counts successfully.

### Vulnerability Scanner Operator Access

HIMP now includes a Vulnerability Scanner sidebar launcher to https://vulnscanner.server.arpa using a safe new-tab link with noopener/noreferrer.

Greenbone itself remains a separate security platform rather than being embedded in HIMP. This avoids weakening Greenbone's frame/security boundaries while giving operators one-click access from HIMP.

### Greenbone Direct HTTPS Management Closure

The Greenbone management host is vulnscanner.server.arpa at 10.10.37.62. Its container nginx remains bound to loopback, while Caddy provides the internal management HTTPS frontend on 10.10.37.62:443.

An internal mkcert-issued certificate was installed under /etc/vulnscanner/tls and Caddy was granted least-required read access to the certificate/key. nftables permits HTTPS only from the approved internal 10.10.37.0/24 and 192.168.37.0/24 networks.

Production validation confirmed Caddy active, Greenbone healthy, HTTPS returning HTTP/2 200, and direct browser access to vulnscanner.server.arpa working without SSH tunneling.

The Greenbone UI is intentionally launched as its own page. HIMP does not iframe or proxy the Greenbone application into the HIMP page.

### Windows Pre-Scan Hardening Work Completed

Before the next Greenbone scan of the Windows workstation at 192.168.37.60, externally reachable listeners were reviewed from the scanner and mapped to their owning Windows processes.

ASUS ArmourySocketServer TCP 9012/9013, ASUS AacAmbientLighting TCP 6850, Hyper-V TCP 2179, RPC TCP 135, VMware TCP 902/912, SMB/NetBIOS TCP 139/445, and other unnecessary listeners were confirmed blocked/filtered from the scanner path after firewall hardening.

UrBackup client exposure on TCP 35621/35623 was restricted to the legitimate UrBackup server at 10.10.37.55; subsequent scanner-side tests showed both ports blocked/filtered from vulnscanner.

Brother WorkflowAppControl TCP 54950 remained the only tested open TCP listener in the final hardened sweep because Brother printer workflow functionality was still in use. The Brother laser printer is 192.168.37.37. Any future restriction should preserve required Brother discovery/update behavior rather than being applied blindly.

### Final Phase 16.3 Validation

Initial Phase 16.3 contract regression: 6 passed.

Initial inventory/web UX regression: 70 passed.

Initial full regression: 1176 passed.

After the Group selector correction: Phase 16.3 contract 7 passed; inventory/web regression 71 passed; full regression 1177 passed in 5.25 seconds.

compileall: PASS.

git diff --check: PASS.

Implementation commit: 650dc4fd46f51956a44f514e92e64db040f703c4 - feat: simplify secure host onboarding.

Regression-fix commit / final application release: 7cbce8faefba8b5804905eb720458a30b729649e - fix: restore inventory group selector.

Final identity: LOCAL = REMOTE = DEPLOYED = 7cbce8faefba8b5804905eb720458a30b729649e.

HIMP service: active/running after deployment; Uvicorn application readiness completed successfully.

Repository/worktree: clean and synchronized.

Production browser validation: PASS for Add Host, SSH Setup existing/legacy path, dedicated himp-automation path, and live Group selector.

### Phase 16.3 Closure Decision

Phase 16.3 - Simplified Secure Host Onboarding is CLOSED as COMPLETE / PRODUCTION VERIFIED. The production HIMP UI now provides deterministic secure onboarding for both legacy hosts and new Linux hosts, preserves the dedicated himp-automation recommendation, validates the actual HIMP service SSH identity, preserves inventory group selection, and provides direct operator navigation to the separately secured Greenbone interface.

### Immediate Next Starting Point

Do not reopen Phase 16.3 unless production evidence identifies a defect. Select the next bounded Phase 16 lifecycle/advanced-operations slice from current production evidence. Preserve the security-first architecture, internal-only integration posture, existing HIMP execution and inventory models, and the one-slice-at-a-time implementation/testing/production-validation workflow.

# Phase 16.3 Vulnerability Intelligence Integration Closure Addendum

Status: COMPLETE / PRODUCTION VERIFIED

This revision records the completed Greenbone-to-HIMP vulnerability intelligence work performed after the secure-host-onboarding closure. Greenbone remains a separate security platform. HIMP now consumes bounded scan evidence through a least-privilege integration path, persists normalized vulnerability intelligence in PostgreSQL, correlates findings to HIMP inventory, and presents the result through authenticated operator-facing HIMP pages.

## 16.3.1 — Greenbone Vulnerability Data Access and Baseline Validation

Status: COMPLETE / PRODUCTION VERIFIED.

Validated Greenbone scan execution and return-path behavior from the dedicated vulnscanner host.

Diagnosed a Greenbone VT cache inconsistency: 95,102 NASL files versus 95,044 Redis NVT/filename keys.

Rebuilt the supported Greenbone VT cache and verified exact 95,102 / 95,102 / 95,102 alignment.

Completed a clean pilot scan of unbound107 with 18 results and no returning VT dependency warnings.

Established a dedicated constrained himp-greenbone integration boundary and read-only report-export path rather than embedding Greenbone or granting broad management access.

## 16.3.2 — Vulnerability Persistence, Import, and Inventory Correlation

Status: COMPLETE / PRODUCTION VERIFIED.

Added the Greenbone read client, vulnerability import service, and PostgreSQL vulnerability repository.

Extended the canonical PostgreSQL schema with vulnerability_reports and vulnerability_findings.

The PostgreSQL table inventory contract now contains exactly 29 expected and 29 actual HIMP tables, with no missing or unexpected schema tables.

Production schema initialization created the vulnerability tables and indexes successfully.

Imported Greenbone report 71b899c6-12f2-4728-9c8c-6de2e352bc98 for unbound107.

The production import persisted 18 unique findings with maximum severity 5.9 and threat counts Log=13, Low=3, Medium=2, High=0, Critical=0.

Inventory correlation resolved the imported scan target to HIMP inventory hostname unbound107.

A second identical production import proved idempotence: one report row, 18 findings, 18 unique result identifiers, and zero duplicate result groups.

Production proof completed with return code 0 while HIMP and the scheduler timer remained healthy.

Phase 16.3.2 validation: PostgreSQL schema tests 9 passed; complete PostgreSQL regression 63 passed; focused tests 9 passed; full regression 1187 passed; compileall PASS; git diff --check PASS.

## 16.3.3 — Vulnerability Intelligence Operator UX

Status: COMPLETE / PRODUCTION VERIFIED.

Added Vulnerability Intelligence presentation logic and authenticated HIMP routes for the overview, report detail, and finding detail surfaces.

Added canonical sidebar navigation to /vulnerabilities.

The production overview displays report count, finding count, severity summary, latest scan evidence, and latest findings with links to detailed evidence.

Production data at final validation: 1 report, 18 findings, 0 critical, 0 high, 2 medium, 3 low; latest host unbound107; maximum severity 5.9 Medium.

Initial implementation validation completed with 11 focused vulnerability-intelligence tests, 24 related page/security tests, and 1198 passing full-regression tests.

Production browser review exposed insufficient contrast in vulnerability cards. The templates were corrected to use the canonical dark-card/light-text presentation and regression coverage was added.

The contrast correction was committed as f49e172 — fix: improve vulnerability card contrast.

Final deployed application identity is LOCAL = REMOTE = DEPLOYED = f49e172b55e0847157e90dbc2a734e4c9d71a954.

Post-deployment HIMP service remained active, the scheduler timer remained active, Uvicorn listened on 127.0.0.1:9347 behind the Phase 16.1 HTTPS boundary, and the unauthenticated vulnerability-page boundary returned HTTP 303.

Final browser validation confirmed the Vulnerability Intelligence page rendered correctly with readable dark-theme contrast and persisted production scan data.

Final Phase 16.3.3 regression/build evidence: 1198 passed; compileall PASS; git diff --check PASS.

## Phase 16.3 Vulnerability Intelligence Closure Decision

The Greenbone vulnerability intelligence integration is CLOSED as COMPLETE / PRODUCTION VERIFIED. HIMP now has a bounded read-only path from Greenbone scan evidence into PostgreSQL-backed, inventory-correlated vulnerability intelligence and an authenticated operator UX. Greenbone remains separately secured and independently managed. The integration does not expose a public callback, does not embed the Greenbone management application, and does not create a second inventory or execution model.

## Immediate Next Starting Point

Do not reopen the completed Phase 16.3 vulnerability persistence or UX slices unless production evidence identifies a defect. Select the next bounded Phase 16 lifecycle/advanced-operations slice from current production evidence. Preserve the security-first, internal-only architecture and the established one-slice-at-a-time implementation, consolidated regression, production validation, Git checkpoint, and authoritative-roadmap update workflow.

# Phase 16.4 - Inventory-Driven Greenbone Vulnerability Onboarding

Status: COMPLETE / PRODUCTION VERIFIED

Phase 16.4 extended the completed Phase 16.3 vulnerability-intelligence integration so HIMP can deterministically onboard eligible inventory hosts into Greenbone while preserving the existing security boundary, scanner self-exclusion, canonical HIMP inventory model, and delta-only reconciliation behavior. The work was implemented as one bounded slice, regression-tested at the end of the slice, committed, pushed, deployed through the canonical release boundary, and live-validated in production.

The design deliberately does not make Greenbone a second source of truth for host inventory. HIMP inventory remains authoritative. Vulnerability onboarding derives the desired Greenbone target state from active HIMP inventory, filters hosts through an explicit eligibility contract, and reconciles only when inventory changes require Greenbone work.

## Implementation Delivered

Added himp/services/vulnerability_onboarding.py as the bounded inventory-to-Greenbone onboarding service.

Extended himp/services/automation.py so the normal inventory synchronization path can invoke vulnerability onboarding without creating a parallel scheduler or inventory subsystem.

Extended himp/services/greenbone.py with the Greenbone reconciliation behavior required by the onboarding service.

Updated canonical inventory/hosts.yml to include the management hosts logs.server.arpa and vulnscanner.server.arpa under the management group.

Added regression coverage in tests/services/test_vulnerability_onboarding.py, tests/services/test_automation_vulnerability_onboarding.py, and tests/services/test_greenbone.py.

Preserved the scanner self-target safety boundary: vulnscanner.server.arpa is explicitly excluded from Greenbone eligibility.

Confirmed logs.server.arpa is an eligible Greenbone target.

Kept the management group outside the maintenance group so management-plane inventory additions do not silently expand scheduled-update scope.

Implemented steady-state delta behavior: unchanged inventory performs zero Greenbone reconciliation calls.

## Management Inventory and Connectivity Proof

During production proof, the management inventory initially exposed two validation-script defects rather than product defects. The first host-count attempt incorrectly counted the Ansible group heading and reported three matches even though the group contained exactly two hosts. The second attempt used a malformed awk expression. The proof was corrected to count the actual host entries without awk.

The corrected HIMP-identity Ansible inventory output showed exactly two management hosts: logs.server.arpa and vulnscanner.server.arpa. MANAGEMENT_MATCHED_HOSTS=2 and MANAGEMENT_HOST_COUNT=PASS.

A real Ansible ping was then executed as the himp service identity using HOME=/var/lib/himp and ANSIBLE_PRIVATE_KEY_FILE=/var/lib/himp/.ssh/id_ed25519. Both logs.server.arpa and vulnscanner.server.arpa returned SUCCESS with ping=pong. MANAGEMENT_ANSIBLE_PING=PASS.

## Eligibility and Safety Contract

Production inventory proof reported ACTIVE_HOSTS=47 and TOTAL_HOSTS=51.

Greenbone eligibility reported GREENBONE_ELIGIBLE_HOSTS=46.

logs.server.arpa: active management host and Greenbone eligible.

vulnscanner.server.arpa: active management host and explicitly excluded from Greenbone targeting.

Management hosts remain outside maintenance: MANAGEMENT_OUTSIDE_MAINTENANCE=PASS and later RUNTIME_MANAGEMENT_OUTSIDE_MAINTENANCE=PASS.

An explicit scanner self-target reconciliation attempt returned RC=1 and SCANNER_SELF_TARGET=DENIED.

Unchanged inventory reconciliation produced GREENBONE_RECONCILE_CALLS=0 and UNCHANGED_INVENTORY_ZERO_CALLS=PASS.

## Regression and Build Validation

Exact implementation changeset: seven files.

Canonical inventory validation: PASS.

Full Python compileall: PASS.

git diff --check: PASS.

Complete HIMP regression: 1220 passed in 5.30 seconds.

Critical Phase 16.4 onboarding slice: 18 passed in 0.09 seconds.

Management safety contract: PASS.

Final system safety before commit: HIMP service active, scheduler timer active, failed units=0.

Worktree stability check: PASS.

## Git Checkpoint

Branch: feature/plugin-sdk.

Commit: 8ac73acda935aea64985a5fffc311d33336c016b.

Subject: feat: add inventory-driven vulnerability onboarding.

Commit scope: 7 files changed, 878 insertions, 1 deletion.

New files: himp/services/vulnerability_onboarding.py; tests/services/test_automation_vulnerability_onboarding.py; tests/services/test_vulnerability_onboarding.py.

After push: LOCAL = REMOTE = 8ac73acda935aea64985a5fffc311d33336c016b.

Post-commit repository worktree: clean and synchronized.

## Production Deployment and Runtime Inventory

The first deployment command attempted ./scripts/deploy.sh, which does not exist in this repository. No release change occurred from that failed command. Deployment was resumed through the established canonical release boundary, scripts/deploy/himp.sh.

The canonical deployment completed successfully. HIMP application files were deployed, systemd units were unchanged, the scheduler timer runtime state was preserved, HIMP was restarted, the application-level readiness gate succeeded, and /opt/himp/.himp-release advanced to the Phase 16.4 commit.

The first post-deployment artifact check correctly exposed an architectural deployment behavior: the canonical deployment preserves persistent runtime inventory and therefore does not overwrite /opt/himp/inventory/hosts.yml with Git inventory changes. This was not bypassed. The approved automation-identity installer was used to install the explicitly approved canonical inventory into the runtime boundary.

The automation-identity installation validated the source inventory, installed the approved runtime inventory, validated the runtime inventory, verified the HIMP SSH identity, and verified non-interactive sudo. The runtime inventory then matched the committed source exactly. A pre-install backup was preserved at /opt/himp/inventory/hosts.yml.pre-himp-automation-identity.

Runtime management group: exactly logs.server.arpa and vulnscanner.server.arpa.

Runtime management host count: 2.

Runtime HIMP-identity Ansible ping: PASS for both management hosts.

Runtime host count: 47.

LOCAL = REMOTE = DEPLOYED = 8ac73acda935aea64985a5fffc311d33336c016b.

HIMP service active; scheduler timer active; failed units=0.

## Final Production Acceptance

Release convergence: LOCAL = REMOTE = DEPLOYED = 8ac73acda935aea64985a5fffc311d33336c016b.

Production inventory: ACTIVE_HOSTS=47; TOTAL_HOSTS=51.

Greenbone eligible inventory: 46 hosts.

LOGS_GREENBONE_ELIGIBLE=PASS.

VULNSCANNER_GREENBONE_EXCLUSION=PASS.

Production steady-state inventory synchronization: synced=47, active_hosts=47, total_hosts=51, recent_changes=25.

Production steady-state Greenbone reconciliation calls: 0.

DEPLOYED_DELTA_ONLY_ZERO_CALLS=PASS.

Runtime management isolation from maintenance: PASS.

One normal scheduler tick completed with code=exited, status=0/SUCCESS.

Scheduler discovered 13 vulnerability reports, imported 0, and reported 0 remaining; this is the expected idempotent steady state because all currently available reports were already imported.

Scheduler evaluation reported Due tasks: 0 and Due remediation schedules: 0.

SCHEDULER_RESULT=success.

Final HIMP service: active.

Final scheduler timer: active.

Final failed systemd units: 0.

Final repository: feature/plugin-sdk synchronized with origin and clean.

PHASE_16_4_FINAL_ACCEPTANCE=PASS.

## Phase 16.4 Closure Decision

Phase 16.4 - Inventory-Driven Greenbone Vulnerability Onboarding is CLOSED as COMPLETE / PRODUCTION VERIFIED. HIMP inventory is now the authoritative driver for bounded Greenbone onboarding. Active eligible hosts can be reconciled without making Greenbone a second inventory authority; the scanner cannot target itself; management hosts remain outside maintenance; unchanged inventory causes zero Greenbone reconciliation calls; and the complete path has been regression-tested, committed, deployed, runtime-aligned, scheduler-exercised, and production-accepted.

## Next Steps

Begin the next bounded Phase 16 vulnerability-operations UX slice without reopening completed Phase 16.3 persistence/UX or Phase 16.4 onboarding unless production evidence identifies a defect.

Add operator filtering/drill-down for vulnerability intelligence in this order: Inventory Group -> Host -> Reports.

Add a Last 3 Report Comparison view for a selected host.

For the three-report comparison, present new findings, resolved findings, unchanged findings, severity changes, finding-count changes, maximum-severity trend, and scan dates using persisted Greenbone/HIMP evidence.

Add a bounded ad-hoc vulnerability scan action from HIMP. The action must use the existing constrained Greenbone boundary, reuse HIMP inventory eligibility, deny scanner self-targeting, remain authenticated/authorized, and avoid creating a second execution or inventory model.

Preserve delta-only onboarding and idempotent report import behavior.

Preserve internal-only security posture: no public callbacks, no external generic webhook expansion, and no embedding of the Greenbone management application.

Continue the established workflow: inspect one bounded slice, implement it end-to-end, consolidate focused/full regression at the end, run compileall and git diff --check, production-validate, create a Git checkpoint, deploy through scripts/deploy/himp.sh, and update this authoritative roadmap.

At the next roadmap closure, record actual commit/release identity, regression count, production scan/report evidence, service/scheduler state, and the exact next-session starting point.

## Next-Session Starting Point

Start by inspecting the existing Vulnerability Intelligence service, repository, routes/templates, Greenbone client/reconciliation APIs, inventory group/host services, and persisted report/finding schema. Define the smallest safe slice for Group -> Host -> Reports filtering and Last 3 Report Comparison before changing code. Do not implement the ad-hoc scan control in the same slice unless the inspection proves it is small, bounded, and can be validated without weakening the current Greenbone safety boundary.

# Roadmap Decision Record - 2026-08-24 Phase 16.4 Closure

Phase 16.4 inventory-driven Greenbone vulnerability onboarding is COMPLETE / PRODUCTION VERIFIED at commit 8ac73acda935aea64985a5fffc311d33336c016b. Final regression is 1220 passing tests, with an 18-test critical onboarding slice, compileall PASS, and git diff --check PASS. Production contains 47 active HIMP hosts of 51 total known hosts and 46 Greenbone-eligible hosts. logs.server.arpa is eligible; vulnscanner.server.arpa is explicitly excluded. The management group contains exactly those two hosts, both are reachable using the actual himp service SSH identity, and management remains outside maintenance. Steady-state inventory synchronization makes zero Greenbone reconciliation calls. The approved runtime inventory was installed through the automation-identity boundary after canonical deployment correctly preserved persistent runtime inventory. Final LOCAL, REMOTE, and DEPLOYED identities all equal 8ac73acda935aea64985a5fffc311d33336c016b. A normal production scheduler tick completed successfully, discovered 13 vulnerability reports, imported 0 already-known reports, left 0 remaining, found no due automation or remediation work, and left HIMP active, the scheduler timer active, and failed units at zero. The next planned bounded work is vulnerability intelligence filtering/drill-down and three-report comparison, followed by a separately bounded ad-hoc scan control using the existing constrained Greenbone boundary.

# Phase 16.5 - Vulnerability Operations UX and Real-Data Functional Acceptance

Status: COMPLETE / PRODUCTION VERIFIED

Phase 16.5 extended the persisted Greenbone/HIMP vulnerability-intelligence surface into operator drill-down and real-data production acceptance. The completed slice preserved the Phase 16.3 persistence model and Phase 16.4 inventory-driven onboarding boundary rather than creating a second vulnerability, inventory, or execution subsystem. Production validation used actual PostgreSQL-backed Greenbone report and finding data and authenticated HIMP web routes.

Implementation and release evidence
The final Phase 16.5 application revision is 9836e82752c3a044e59c7c100ae4736d2c3d15ba. Final verification proved LOCAL = REMOTE = DEPLOYED at that revision on branch feature/plugin-sdk. HIMP remained active, the scheduler timer remained active, failed systemd units remained zero, and the repository was clean and synchronized. The final Phase 16.5 regression baseline is 1228 passing tests, with compileall and git diff --check passing.

Phase 16.5 operator behavior
The vulnerability operations UX provides authenticated inventory-host vulnerability drill-down using persisted report and finding evidence. Host presentation includes scan reports, finding counts, maximum severity, scan timestamps, report-detail links, finding-detail links, and the actual persisted finding names/severity evidence. The work remains read-only with respect to vulnerability evidence during normal presentation and does not weaken the constrained Greenbone boundary.

Production PostgreSQL real-data discovery
An initial acceptance probe reported zero persisted reports because it did not load the production PostgreSQL environment. That result was correctly treated as a validation-script/environment defect rather than evidence that production vulnerability data was absent. The corrected inspection explicitly loaded the production database environment and proved DATABASE_BACKEND=postgresql.

The corrected production inspection found 14 vulnerability reports and 436 persisted findings mapped across 12 inventory hosts. Mapped hosts were automation.server.arpa, dns1009, dns1011, dns1013, dns1070, dns1071, emby, unbound1007, unbound1008, unbound107, unbound108, and unbound37100. Maximum observed severity among these reports was 8.1 on emby. automation.server.arpa contained 62 findings with maximum severity 5.3. The DNS hosts contained up to 48 findings with maximum severity 5.9. unbound107 contained 22 findings across three persisted reports with maximum severity 5.9.

Authentication-boundary validation
The first unauthenticated route probe used HTTP HEAD and returned 405. Inspection proved this was a method-contract issue rather than an authentication defect: HEAD returned 405 while the correct unauthenticated GET returned HTTP 303 with Location: /login. The login page returned HTTP 200. Inspection of the deployed login JavaScript confirmed the exact authentication contract: POST /api/auth/login, Content-Type application/json, credentials same-origin, and JSON username/password fields.

Authenticated real-data acceptance
Using credentials captured locally without echoing the password, the production acceptance authenticated through the exact deployed /api/auth/login contract and established a valid session. GET of the real host vulnerability page for unbound107 returned HTTP 200. The rendered page proved the real host identity, vulnerability presentation, report table, findings table, scan timestamps, severity evidence, and drill-down navigation.

The unbound107 page rendered three report links and 22 finding links. Persisted evidence included the 2026-08-24 18:10:09 scan, HIMP Pilot - unbound107 - Full and Fast, maximum severity 5.9, and the medium-severity finding Prefix Truncation Attacks in SSH Specification (Terrapin Attack). Additional rendered evidence included OS Detection Consolidation and Reporting and Hostname Determination Reporting findings. The authenticated response did not redirect to /login.

Sensitive-session cleanup and mutation safety
Temporary login/session artifacts were removed after validation. Final release and runtime checks again proved LOCAL = REMOTE = DEPLOYED = 9836e82752c3a044e59c7c100ae4736d2c3d15ba, HIMP active, scheduler timer active, failed units=0, and a clean synchronized worktree. The production acceptance performed no source mutation.

Phase 16.5 Closure Decision
Phase 16.5 - Vulnerability Operations UX and Real-Data Functional Acceptance is CLOSED as COMPLETE / PRODUCTION VERIFIED. The host-level vulnerability presentation is now proven against real PostgreSQL-backed Greenbone evidence through the deployed authenticated HIMP web contract. Authentication protection, login behavior, host identity, report/finding presentation, drill-down links, release convergence, service health, scheduler health, cleanup, and non-mutation safety all passed.

Next Bounded Phase 16 Work
Do not reopen Phase 16.5 unless production evidence identifies a defect. The next bounded vulnerability-operations slice should build on the persisted host/report/finding evidence already proven in production. The previously planned Last 3 Report Comparison remains a strong next candidate: for a selected host, compare the latest three persisted reports and present new findings, resolved findings, unchanged findings, severity changes, finding-count changes, maximum-severity trend, and scan dates. Keep any ad-hoc scan action as a separately bounded slice unless inspection proves it can be implemented and validated without weakening Greenbone self-target denial, inventory eligibility, authentication/authorization, or the existing constrained integration boundary.

## Roadmap Decision Record - 2026-08-24 Phase 16.5 Closure

Phase 16.5 vulnerability operations UX and real-data functional acceptance is COMPLETE / PRODUCTION VERIFIED at revision 9836e82752c3a044e59c7c100ae4736d2c3d15ba. Final regression is 1228 passing tests with compileall PASS and git diff --check PASS. Production PostgreSQL inspection proved 14 vulnerability reports, 436 findings, and 12 mapped inventory hosts. Authenticated web acceptance against unbound107 returned HTTP 200 and rendered three persisted report links plus 22 finding links. The unauthenticated GET boundary returned HTTP 303 to /login; the deployed login page and POST /api/auth/login JSON contract were verified. Final LOCAL, REMOTE, and DEPLOYED identities converged, HIMP and the scheduler timer were active, failed units were zero, temporary session data was removed, and the repository remained clean and synchronized. The next preferred bounded Phase 16 slice is the Last 3 Report Comparison for a selected host, with ad-hoc scan execution retained as separate follow-on work.

# Phase 16.6 - Vulnerability Historical Comparison and PDF/TXT/CSV Reporting

Status: COMPLETE / PRODUCTION VERIFIED

Phase 16.6 converted the persisted host-level vulnerability evidence proven in Phase 16.5 into historical change intelligence and exportable operator reports. The slice remained read-only with respect to Greenbone scan execution and reused the existing PostgreSQL vulnerability repository, authenticated HIMP web boundary, inventory-correlated report/finding model, and established HIMP reporting patterns. No parallel vulnerability database, report store, inventory model, or execution engine was introduced.

## Production Evidence Used to Define the Comparison Contract

Before implementation, production PostgreSQL data was inspected through the exact HIMP database environment at /etc/himp/database.env. At that checkpoint the production store contained 17 vulnerability reports and 542 findings. The selected acceptance host, unbound107, had exactly three persisted reports.

Newest report 71b899c6-12f2-4728-9c8c-6de2e352bc98 — finished 2026-08-24 18:10:09; 18 findings; maximum severity 5.9.

Previous report 339f7c45-bd07-485c-a666-71e4c7cfc479 — finished 2026-08-24 17:24:06; 4 findings; maximum severity 0.0.

Oldest report abf68466-1563-44a8-a90f-8f42cb3a52c0 — finished 2026-08-24 15:23:44; 0 findings; maximum severity 0.0.

Finding continuity was validated against real data using the tuple (nvt_oid, port). Across all three unbound107 reports, duplicate identities=0 and missing nvt_oid=0.

The newest-vs-previous real-data comparison produced 14 introduced findings, 4 persistent findings, 0 resolved findings, 0 severity increases, 0 severity decreases, and a finding-count delta of +14.

## Implementation Delivered

Added himp/services/vulnerability_comparison.py to provide deterministic historical host comparison over persisted vulnerability reports and findings.

Comparison identity uses Greenbone NVT OID plus port/protocol value, with a deterministic name-based fallback for older/manual persisted evidence lacking an NVT OID.

Host comparison returns up to the latest three persisted reports and pairwise comparisons ordered newest-first.

Comparison categories include introduced, resolved, persistent, severity increased, severity decreased, severity unchanged, finding-count delta, and maximum-severity trend.

Added himp/services/vulnerability_report_export.py to generate vulnerability intelligence exports in PDF, TXT, and CSV formats from persisted HIMP data.

PDF export provides a human-readable HIMP Vulnerability Intelligence Report containing host summary, severity counts, latest report history, latest-vs-previous comparison summary, and current findings.

TXT export provides the same operational evidence in a copy/paste-friendly text format for tickets, email, troubleshooting, or archival.

CSV export provides structured finding-level fields including hostname, report_id, result_id, nvt_oid, finding_name, port, severity, threat, qod, and change_status.

Extended the authenticated host vulnerability page with Historical Comparison presentation and Export PDF / Export TXT / Export CSV controls.

Added authenticated GET export routes at /api/vulnerabilities/hosts/{hostname}/pdf, /txt, and /csv.

The implementation remained read-only toward Greenbone; Phase 16.6 did not add ad-hoc scan execution and did not change the Phase 16.4 delta-only onboarding contract.

## Historical Comparison Operator Contract

For a host with at least two persisted reports, the host vulnerability page now presents the latest-vs-previous delta directly in HIMP. Operators can see the count and details of newly introduced findings, resolved findings, persistent findings, finding-count change, and any severity increases or decreases. When fewer than two reports exist, the UI explicitly states that at least two persisted vulnerability reports are required for historical comparison rather than manufacturing a trend.

## Export and Authentication Contract

PDF media type: application/pdf with attachment filename <hostname>-vulnerabilities.pdf.

TXT media type: text/plain; charset=utf-8 with attachment filename <hostname>-vulnerabilities.txt.

CSV media type: text/csv; charset=utf-8 with attachment filename <hostname>-vulnerabilities.csv.

All three export routes inherit the existing authenticated HIMP session boundary.

Production unauthenticated requests to PDF, TXT, and CSV export routes each returned HTTP 401.

No Greenbone credential, management interface, or externally exposed callback is required for report export; exports are generated from persisted HIMP evidence.

## Regression and Build Validation

Focused comparison service contract: 5 passed.

Focused vulnerability export service contract: 3 passed.

Authenticated vulnerability export API contract: 4 passed.

Vulnerability UI contract: 12 passed.

Existing HIMP report/export regression: 17 passed.

Combined critical Phase 16.6 slice: 41 passed.

Complete HIMP regression: 1241 passed in 5.56 seconds.

Full compileall: PASS.

git diff --check: PASS.

Regression execution did not mutate the eight-file Phase 16.6 worktree.

## Git Checkpoint and Deployment

Branch: feature/plugin-sdk.

Implementation commit: 745e26ade3d375d90a5462a2b6f04d25bac0158f.

Subject: feat: add vulnerability comparison and exports.

Commit scope: 8 files changed, 2560 insertions.

New services: himp/services/vulnerability_comparison.py and himp/services/vulnerability_report_export.py.

New tests: tests/api/test_vulnerability_exports.py, tests/services/test_vulnerability_comparison.py, and tests/services/test_vulnerability_report_export.py; existing vulnerability page tests were extended.

Deployment used the canonical release boundary scripts/deploy/himp.sh.

Post-deployment LOCAL = REMOTE = DEPLOYED = 745e26ade3d375d90a5462a2b6f04d25bac0158f.

HIMP application readiness returned HTTP 303 at the loopback root after restart; HIMP service active; scheduler timer active; failed units=0.

OpenAPI verification proved GET registration for all three export routes.

A normal scheduler tick completed with Result=success, discovered 17 vulnerability reports, imported 0 already-known reports, left 0 remaining, and found no due automation or remediation work.

## Final Real-Data Production Acceptance

Production comparison for unbound107 returned REPORT_COUNT=3 with the expected three persisted report identifiers and scan timestamps.

Latest-vs-previous production comparison returned INTRODUCED=14, PERSISTENT=4, RESOLVED=0, SEVERITY_INCREASED=0, SEVERITY_DECREASED=0, and FINDING_COUNT_DELTA=14.

The authenticated host page returned HTTP 200 and rendered Historical Comparison, New Findings, Resolved, Persistent, Finding Delta, and the real Prefix Truncation Attacks in SSH Specification (Terrapin Attack) finding.

PDF export returned HTTP 200, valid %PDF- magic, and a 4262-byte production file.

TXT export returned HTTP 200 and contained Host: unbound107, Reports: 3, Findings: 22, Introduced: 14, Resolved: 0, Persistent: 4, severity-change counters, and the Terrapin finding.

CSV export returned HTTP 200 and parsed successfully with 22 finding rows and the required structured columns.

CSV change_status distribution during acceptance was NEW=14, UNCHANGED=4, and blank=4. The blank rows are older historical finding records included by the host-level aggregate; the latest-vs-previous comparison itself remains internally consistent at 14 new + 4 unchanged = 18 newest-report findings.

CSV contained exactly one Terrapin row during acceptance.

Temporary session, login-response, rendered host-page, PDF, TXT, and CSV validation files were removed after acceptance.

Final repository state remained clean and synchronized; HIMP active; scheduler timer active; failed units=0; no source mutation occurred.

## Validation Notes and Non-Blocking Observations

Short-lived standalone Python inspection/acceptance processes emitted PostgreSQL pool shutdown warnings indicating worker threads did not stop within five seconds. These messages did not correspond to a HIMP service failure: the production service and scheduler remained healthy with zero failed units. Future standalone database probes should explicitly close the shared pool or use a context-managed lifecycle to avoid noisy shutdown diagnostics.

The CSV historical blank change_status rows are recorded as a reporting-model nuance rather than a Phase 16.6 correctness failure. A future bounded export-polish slice may choose either current-report-only CSV rows or explicit historical-status labeling if operator need justifies the change.

## Phase 16.6 Closure Decision

Phase 16.6 - Vulnerability Historical Comparison and PDF/TXT/CSV Reporting is CLOSED as COMPLETE / PRODUCTION VERIFIED. HIMP can now explain how a host vulnerability posture changed between persisted scans and export the resulting vulnerability intelligence in human-readable PDF/TXT and structured CSV formats. The feature is authenticated, production-validated against real PostgreSQL/Greenbone evidence, regression-covered, deployed through the canonical release boundary, and preserves the existing internal-only, least-privilege Greenbone architecture.

## Next Bounded Phase 16 Work

Do not reopen Phase 16.6 unless production evidence identifies a defect. The next preferred bounded slice is Phase 16.7 - Bounded Ad-Hoc Vulnerability Scan Execution from HIMP. That work is intentionally separate because it changes infrastructure state by initiating Greenbone scan activity rather than only reading persisted evidence.

Reuse HIMP inventory as the authoritative target source and reuse the Phase 16.4 eligibility contract.

Deny vulnscanner.server.arpa self-targeting through the existing scanner-exclusion safety boundary.

Use the existing constrained himp-greenbone integration instead of broad Greenbone management credentials.

Require HIMP authentication and appropriate authorization for scan initiation.

Create an explicit execution/audit record so operators can see who initiated a scan, the selected host, start/result state, and failure evidence.

Prevent duplicate/overlapping scan initiation for the same bounded target where practical.

Do not create a second inventory model, scheduler, or vulnerability persistence layer.

Keep Greenbone management internal-only; no public callbacks, external generic webhooks, or embedded Greenbone UI.

After implementation, use the established end-to-end workflow: focused/full regression, compileall, git diff --check, commit/push, canonical deployment, real production scan validation, cleanup, and authoritative-roadmap update.

# Roadmap Decision Record - 2026-08-24 Phase 16.6 Closure

Phase 16.6 vulnerability historical comparison and PDF/TXT/CSV reporting is COMPLETE / PRODUCTION VERIFIED at application revision 745e26ade3d375d90a5462a2b6f04d25bac0158f. The final full regression baseline is 1241 passing tests with a 41-test critical Phase 16.6 slice, compileall PASS, and git diff --check PASS. Production PostgreSQL contained 17 reports and 542 findings during the comparison-contract inspection. The production acceptance host unbound107 had three persisted reports; the latest-vs-previous comparison produced 14 introduced, 4 persistent, and 0 resolved findings with a +14 finding-count delta. Authenticated host-page validation rendered the historical comparison and real Terrapin finding. Unauthenticated PDF/TXT/CSV requests returned HTTP 401. Authenticated PDF, TXT, and CSV exports all returned HTTP 200; the PDF had valid %PDF- magic, TXT contained the real comparison evidence, and CSV parsed 22 rows with the required structured schema. Final LOCAL, REMOTE, and DEPLOYED identities all equal 745e26ade3d375d90a5462a2b6f04d25bac0158f. HIMP and the scheduler timer were active, failed units were zero, temporary validation artifacts were removed, and the repository remained clean and synchronized. The next preferred bounded Phase 16 slice is authenticated, auditable ad-hoc vulnerability scan execution from HIMP using the existing inventory eligibility and constrained Greenbone safety boundary.

## Phase 16.6 Post-Deployment Production Correction

Status: COMPLETE / production accepted

Phase 16.6 vulnerability historical comparison and PDF/TXT/CSV host exports were deployed and production-accepted.

A post-deployment export semantics defect was identified: host exports could aggregate findings from report history instead of limiting Current Findings and severity totals to the latest report.

Corrective commit e681b3f7e262654bd72c89f9b8b7cb6b8070ed83 (fix: export latest vulnerability report findings) was committed, pushed, and deployed through the canonical release boundary.

Full regression after the correction: 1,243 tests passed. Critical export slice: 43 tests passed.

Production acceptance on jellyfin: 1 report, 31 current findings, severity totals Critical 2 / High 2 / Medium 5 / Low 5 / Log 17, and singular 'Latest Report' presentation.

Production acceptance on unbound107: 3-report history retained, 18 current findings exported, historical comparison retained at 14 introduced / 4 persistent / 0 resolved.

TXT and CSV exports were validated against current-report-only semantics; Jellyfin CSV contained 31 rows and unbound107 CSV contained 18 rows.

PDF exports for both hosts were validated as real PDF documents.

Final production state: LOCAL = REMOTE = DEPLOYED at e681b3f7e262654bd72c89f9b8b7cb6b8070ed83; HIMP active; scheduler timer active; failed units = 0; repository clean.

Known non-service test noise remains from short-lived standalone PostgreSQL probe processes reporting pool worker shutdown warnings; production HIMP service health was unaffected.

## Next Security Follow-up - Jellyfin SSH Findings

A Greenbone scan of the Jellyfin host reported multiple OpenSSH findings on TCP/22, including critical/high RCE and DoS findings and Terrapin-related findings. These findings require host-level package/version and effective sshd configuration verification before remediation decisions. Password authentication is an explicit operational requirement and should be preserved during remediation.

Planned approach: identify the operating system and vendor package version, compare the installed OpenSSH package against vendor security-fixed versions, inspect effective sshd algorithms and authentication settings, apply supported security updates and targeted cryptographic hardening, preserve password login, validate SSH access before ending the existing administrative session, then rescan with Greenbone/HIMP.

# Phase 16.7 - Bounded Ad-Hoc Vulnerability Scan Execution from HIMP

Status: COMPLETE / PRODUCTION VERIFIED

Phase 16.7 added authenticated, bounded vulnerability scan initiation while preserving HIMP inventory as the authoritative target source and the existing constrained Greenbone integration. The implementation did not create a second inventory, scheduler, or vulnerability persistence model and retained scanner self-target denial and operator-controlled scan execution.

## Phase 16.7.5 - Greenbone Administrator Visibility Lifecycle

Status: COMPLETE / PRODUCTION VERIFIED

Phase 16.7.5 corrected the lifecycle of HIMP-created Greenbone resources so administrator visibility is reconciled deterministically for both the managed target and task. The correction was validated against logs.server.arpa at 10.10.37.58 and then proven idempotent before source control closure.

## Production Admin-Visibility and Idempotence Proof

Production validation host: logs.server.arpa (10.10.37.58).

Existing Greenbone target UUID: c56fe0c4-6f21-450c-b4ff-16f28d75202c.

Existing Greenbone task UUID: c5673258-e460-4059-922d-9e9e694956ad.

A second host-reconcile reported TARGET_EXISTING and TASK_EXISTING; no target or task was recreated.

Administrator visibility was already present for both resources: get_targets on the target and get_tasks on the task.

The permission count remained exactly 2, proving the reconcile did not duplicate role permissions.

The exact permission rows remained one get_targets permission for the target and one get_tasks permission for the task, both assigned to role subject 1.

TARGET_CREATED=NO, TASK_CREATED=NO, MANIFEST_UPDATED=NO, TARGET_ADMIN_VISIBILITY=EXISTING, TASK_ADMIN_VISIBILITY=EXISTING.

SCAN_STARTED=NO and HOST_RECONCILE=PASS.

The task remained unstarted after reconciliation: run_status=2 with empty start_time and end_time.

## Regression and Build Validation

Focused Greenbone regression: 36 passed.

Complete HIMP regression: 1,278 passed in 5.45 seconds.

Python compileall: PASS.

Greenbone helper shell validation: PASS.

config/greenbone/himp-greenbone.sudoers: parsed OK.

git diff --check: PASS.

Expected change set only: scripts/greenbone/himp_greenbone.py and tests/deployment/test_greenbone_helper_install.py.

Change summary: 2 files changed, 262 insertions.

## Git Checkpoint and Source/Live Parity

Branch: feature/plugin-sdk.

Commit: 6d0aa5eaea3a1fa812e54857acb5cdb2e31f2f2d.

Subject: fix: reconcile Greenbone admin visibility.

After push, LOCAL = REMOTE = 6d0aa5eaea3a1fa812e54857acb5cdb2e31f2f2d.

Repository/worktree: clean and synchronized.

Committed Greenbone helper SHA-256: 623b3f363368d2ec999e48e847c1e177f4025711190d7f54935b5334e085404a.

Live vulnscanner helper SHA-256: 623b3f363368d2ec999e48e847c1e177f4025711190d7f54935b5334e085404a.

HELPER_PARITY=PASS.

## Phase 16.7.5 Closure Decision

Phase 16.7.5 is CLOSED as COMPLETE / PRODUCTION VERIFIED. HIMP-managed Greenbone target and task resources now reconcile administrator visibility without duplicating permissions, recreating existing resources, mutating the manifest unnecessarily, or starting a scan as a side effect. The final source-control checkpoint is synchronized at 6d0aa5eaea3a1fa812e54857acb5cdb2e31f2f2d, the complete regression baseline is 1,278 passing tests, and the committed helper is byte-for-byte identical to the helper installed on vulnscanner.

# Roadmap Decision Record - 2026-08-25 Phase 16.7.5 Closure

Phase 16.7 bounded ad-hoc vulnerability scanning is COMPLETE / PRODUCTION VERIFIED, and the Phase 16.7.5 administrator-visibility lifecycle correction is closed at commit 6d0aa5eaea3a1fa812e54857acb5cdb2e31f2f2d. Production idempotence validation against logs.server.arpa proved the existing target and task were preserved, exactly two required role permissions remained present, no duplicate permissions were created, the manifest was not rewritten, and no scan was started. The task remained unstarted. Final validation completed with 36 focused Greenbone tests, 1,278 full-suite tests, compileall PASS, shell/sudoers validation PASS, git diff --check PASS, a clean synchronized repository, and exact SHA-256 parity between the committed and live Greenbone helper.

## Phase 16.7.6 - Inventory Vulnerability Scan Control

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 16.7.6 moved the existing bounded ad-hoc Greenbone scan capability into the HIMP Inventory operator workflow. The implementation reuses the existing authenticated/admin-only vulnerability rescan API and constrained Greenbone host-start boundary; it does not expose Greenbone task identifiers to the browser, create a second execution model, or weaken the existing inventory eligibility and scanner self-target protections.

The Inventory page now presents an administrator-only Vulnerability Scan control with an active-host dropdown and Start Scan action.

The host selector displays HIMP inventory hostname and IP address while the browser submits the hostname through the existing HIMP vulnerability rescan contract.

The control provides operator feedback for scan start, already-active state, and errors while preventing repeated clicks during request processing.

Non-administrator presentation remains bounded by the existing session role context.

Production browser acceptance confirmed logs.server.arpa (10.10.37.58) could be selected from the Inventory dropdown and a vulnerability scan could be started successfully from HIMP.

The production control reported: Vulnerability scan started for logs.server.arpa.

A follow-up UX polish increased the scan instruction text using Bootstrap fs-5, fw-semibold, text-light, and mb-4 classes without changing scan behavior.

### Phase 16.7.6 Validation and Release Checkpoint

Inventory scan UI regression: 4 passed.

Vulnerability rescan regression: 17 passed.

Greenbone boundary regression: 36 passed.

Full regression: 1,282 passed in 5.64 seconds.

compileall: PASS.

git diff --check: PASS.

Implementation commit: bdc36d0d7e51592533fb4d3ffc829c0c81b16309 - feat: add inventory vulnerability scan control.

Implementation release parity: LOCAL = REMOTE = DEPLOYED = bdc36d0d7e51592533fb4d3ffc829c0c81b16309.

UX polish commit/final application release: ac4287f143ccc40b71a7c32c24ced7585801b6cc - style: improve inventory scan control readability.

Final release parity: LOCAL = REMOTE = DEPLOYED = ac4287f143ccc40b71a7c32c24ced7585801b6cc.

HIMP service after final deployment: active/running; application readiness completed successfully.

Scheduler timer remained enabled and active; normal deployment preserved its runtime state.

Final repository/worktree before documentation: feature/plugin-sdk synchronized with origin and clean.

### Phase 16.7.6 Closure Decision

Phase 16.7.6 is CLOSED as COMPLETE / PRODUCTION VERIFIED. Administrators can now initiate a bounded Greenbone vulnerability scan directly from HIMP Inventory by selecting an active host and using Start Scan. Production acceptance proved the operator path against logs.server.arpa, while the implementation continues to reuse HIMP inventory authority, authentication/authorization, and the constrained Greenbone integration boundary. The final application release is ac4287f143ccc40b71a7c32c24ced7585801b6cc with a 1,282-test full regression baseline.

### Next-Session Starting Point

Resume from the clean Phase 16.7.6 production checkpoint. Do not reopen Phase 16.7, 16.7.5, or 16.7.6 unless production evidence identifies a defect. Begin the next bounded Phase 16 lifecycle/advanced-operations slice from current production evidence, preserving the established one-slice-at-a-time workflow, internal-only security posture, HIMP inventory authority, constrained Greenbone boundary, regression gate, production validation, Git checkpoint, deployment parity, and authoritative-roadmap update process.

# Phase 16.8 - Lifecycle & Operations Visibility

Status: ACTIVE — Phase 16.8.1 and Phase 16.8.2 COMPLETE / PRODUCTION VERIFIED.

Phase 16.8 begins the lifecycle and operations visibility work selected from current production evidence. The phase reuses HIMP's existing health, scheduler, maintenance, infrastructure, dashboard, and release-boundary contracts rather than creating parallel monitoring or operations subsystems.

## Phase 16.8.1 - Application Operations Overview

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 16.8.1 expanded the existing /application-health surface into a consolidated Application Operations overview. The implementation is primarily read-only and preserves the existing application health contract while adding bounded lifecycle and operations visibility. Detailed actions remain on their owning HIMP pages.

Preserved the existing application-health status and components contract for backward compatibility.

Added deployed-release visibility sourced from /opt/himp/.himp-release. The release marker is informational and does not affect overall application health.

Retained the existing Database, Scheduler, Automation, Configuration, and Storage component-health presentation.

Added Scheduler Operations visibility with total/enabled/disabled counts, last-run failure state, per-task frequency, last execution evidence, and next-run information.

Added read-only Maintenance State visibility for active and upcoming maintenance windows, with management actions remaining on the Automation page.

Added Infrastructure Health visibility using the existing host-health dashboard contract, including PASS, WARNING, FAIL, UNKNOWN, total-host, and score information.

Added operational navigation to the owning Automation, Health, Inventory, Remediation, Notifications, and Settings surfaces rather than duplicating their controls.

Added the canonical Operations sidebar entry, positioned with the existing health/workflow operator navigation.

Operational collectors are failure-isolated so an optional lifecycle/operations collector cannot prevent the core Application Health page from rendering.

No new database tables, scheduler engine, health engine, maintenance engine, monitoring daemon, or separate /operations application surface was introduced.

### Phase 16.8.1 Validation and Release Checkpoint

Application Health service contract regression: 12 passed during the service-foundation gate.

Expanded Application Health regression after UI/contract integration: 15 passed at the compatibility gate.

Final complete HIMP regression: 1,290 passed.

Python compile validation / compileall: PASS.

git diff --check: PASS.

Implementation commit: 85f1d1f — feat: add application operations overview.

Production UX/navigation correction and final deployed application release: f0cdf75773f91623714810668e0f44391c8cb4b4.

Final production Application Operations page rendered successfully at /application-health.

Production release card displayed f0cdf75773f91623714810668e0f44391c8cb4b4 from the canonical HIMP deployment marker.

Production Application Status displayed HEALTHY.

Production component cards displayed healthy Database, Scheduler, Automation, Configuration, and Storage state.

Production Scheduler Operations displayed 6 schedules, 6 enabled, 0 disabled, and 0 last-run failures.

Operations sidebar navigation and Manage Automation navigation were visually verified.

Production browser acceptance found no visible clipping, overlapping cards, malformed tables, or broken dark-theme presentation.

HIMP production application remained active/running after deployment.

### Phase 16.8.1 Production Acceptance

Final browser acceptance on 2026-08-27 confirmed the production Application Operations page was usable and consistent with the canonical HIMP operator interface. The page showed overall HEALTHY state, the deployed release identity, healthy core components, and live scheduler operations. The Operations sidebar entry was present between Health and Workflows. The scheduler summary showed 6 total schedules, all 6 enabled, 0 disabled, and 0 failed last runs, with per-task last/next execution evidence rendered in the operations table.

### Phase 16.8.1 Closure Decision

Phase 16.8.1 - Application Operations Overview is CLOSED as COMPLETE / PRODUCTION VERIFIED. HIMP now provides a consolidated read-only lifecycle and operations view without duplicating the existing scheduler, health, maintenance, inventory, remediation, notification, or settings control surfaces. The final deployed application revision is f0cdf75773f91623714810668e0f44391c8cb4b4 and the final full regression baseline is 1,290 passing tests.

### Next-Session Starting Point

Resume from the clean Phase 16.8.1 production checkpoint. Do not reopen Phase 16.8.1 unless production evidence identifies a defect. Select the next bounded Phase 16.8 lifecycle/advanced-operations slice from current production evidence. Preserve the one-slice-at-a-time workflow: inspect the existing contracts first, implement one coherent slice end-to-end, run focused and full regression plus compileall and git diff --check, production-validate, create the Git checkpoint, deploy through scripts/deploy/himp.sh, and update this authoritative roadmap at closure. Continue the internal-only, security-first integration posture.

### Roadmap Decision Record - 2026-08-27 Phase 16.8.1 Closure

Phase 16.8.1 Application Operations Overview is COMPLETE / PRODUCTION VERIFIED. The existing /application-health page was expanded into the canonical Application Operations surface with deployed release visibility, application component health, scheduler operations, maintenance state, infrastructure health, and navigation to owning operator pages. The implementation preserved existing service contracts and introduced no parallel monitoring or operations subsystem. Final full regression is 1,290 passing tests with compile/build and diff validation passing. Production browser acceptance confirmed HEALTHY application state, release f0cdf75773f91623714810668e0f44391c8cb4b4, 6 enabled scheduler definitions, zero disabled schedules, zero last-run failures, correct Operations sidebar navigation, and clean dark-theme rendering. Phase 16 remains active; the next work should be selected as another bounded lifecycle/advanced-operations slice from current production evidence.

## Phase 16.8.2 - Operational Attention Overview

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 16.8.2 extended the existing Application Operations page with a consolidated read-only Operational Attention section. The slice deliberately reused DashboardService.operational_summary() at the page-composition boundary instead of creating another monitoring, alerting, remediation, or status engine.

Composed the existing dashboard operational summary into the /application-health page route while keeping ApplicationHealthService and DashboardService independently owned.

Added an Operational Attention section between the Maintenance/Infrastructure row and Operational Navigation.

Rendered the aggregate PASS, WARNING, or FAIL state from the existing dashboard operational-summary contract.

Rendered individual attention items with severity, category, operator-facing message, and a link to the owning HIMP page.

Supported a clean PASS empty state: No current operational conditions require attention.

Reused existing host-health, workflow, automation, and remediation attention calculations; no duplicate warning logic was introduced.

Detailed actions remain on their owning pages such as Health, Automation, and Remediation.

No new database tables, notification engine, scheduler behavior, remediation logic, monitoring daemon, or separate operations subsystem was introduced.

Existing page tests were hardened so every route-based Application Operations test explicitly owns both the Application Health and Dashboard operational-summary inputs.

### Phase 16.8.2 Validation and Release Checkpoint

Application Operations page regression: 5 passed.

Dashboard operational-summary regression: 18 passed.

Complete Application Health regression: 18 passed.

Related Dashboard + Application Health regression: 36 passed.

Final complete HIMP regression: 1,292 passed.

Python compile validation / compileall: PASS.

git diff --check: PASS.

Merge-marker and exact three-file scope gates: PASS.

Implementation commit: 9fcca8908f8525c323154849e985e0dc8297974e - feat: add operational attention overview.

Implementation scope: himp/api/server.py, templates/application_health.html, and tests/api/test_application_health_page.py.

Release parity after deployment: LOCAL = REMOTE = DEPLOYED = 9fcca8908f8525c323154849e985e0dc8297974e.

HIMP and Caddy services remained active after deployment; listeners on 127.0.0.1:9347 and :443 were verified.

Live Application Operations render returned HTTP 200 and included Operational Attention.

Recent HIMP error inspection after deployment found no error, exception, traceback, or critical entries.

Final repository/worktree before documentation closure was synchronized and clean.

### Phase 16.8.2 Production Acceptance

Production acceptance on 2026-08-27 verified both healthy and exception behavior. Immediately after deployment, the live Dashboard operational-summary contract reported PASS with zero attention items and the Application Operations route rendered successfully. Final browser acceptance then captured live infrastructure state with 47 inventory hosts: 46 passed, 1 failed, 0 warnings, 0 unknown, and a 98% infrastructure score. Operational Attention dynamically changed to FAIL and displayed a Host Connectivity item stating that 1 host failed connectivity checks. The section rendered cleanly above Operational Navigation with readable severity badges and no visible clipping, overlap, or malformed layout.

### Phase 16.8.2 Closure Decision

Phase 16.8.2 - Operational Attention Overview is CLOSED as COMPLETE / PRODUCTION VERIFIED. HIMP now provides a consolidated operator-attention layer on the canonical Application Operations page while preserving the existing dashboard as the authoritative attention aggregation. The final deployed application revision is 9fcca8908f8525c323154849e985e0dc8297974e and the final full regression baseline is 1,292 passing tests.

### Next-Session Starting Point

Resume from the clean Phase 16.8.2 production checkpoint. Do not reopen Phase 16.8.1 or Phase 16.8.2 unless production evidence identifies a defect. Select the next bounded Phase 16.8 lifecycle/advanced-operations slice from current production evidence rather than inventing a parallel subsystem. Preserve the one-slice-at-a-time workflow: inspect existing contracts first, implement one coherent slice end-to-end, run focused and full regression plus compileall and git diff --check, production-validate, create the Git checkpoint, deploy through scripts/deploy/himp.sh, and update this authoritative roadmap at closure. Continue the internal-only, security-first integration posture.

### Roadmap Decision Record - 2026-08-27 Phase 16.8.2 Closure

Phase 16.8.2 Operational Attention Overview is COMPLETE / PRODUCTION VERIFIED. The existing /application-health Application Operations surface now consumes the authoritative DashboardService.operational_summary() contract at the page-composition boundary and presents current operator-attention conditions without duplicating health, workflow, automation, remediation, notification, or alerting logic. Final full regression is 1,292 passing tests with compileall, diff, merge-marker, and scope validation passing. Production browser acceptance proved dynamic FAIL behavior from live infrastructure evidence: 47 inventory hosts, 46 passed, 1 failed, 0 warnings, 0 unknown, 98% score, and a Host Connectivity attention item for the failed host. Final deployed application revision is 9fcca8908f8525c323154849e985e0dc8297974e. Phase 16 remains active; the next work should be selected as another bounded lifecycle/advanced-operations slice from current production evidence.

## Phase 16.8.3 - Operator Guidance, Self-Help & Continuity

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 16.8.3 extended the existing Application Operations and Operational Attention surface with reviewed, deterministic operator guidance intended to make HIMP safer and more understandable for a non-technical continuity operator. The slice remained read-only and deliberately avoided runtime generative guidance, automated remediation, duplicate operational logic, or a parallel alerting subsystem.

Added a Git-managed operator guidance catalog at config/operator_guidance.yml.

Added OperatorGuidanceService with strict catalog validation and deterministic mapping from the existing Dashboard operational-attention contract.

Kept the guidance layer informational only: no reboot, restart, shell, SSH, Ansible, remediation execution, scheduler mutation, firewall, DNS, storage, or virtualization control was added.

Integrated guidance at the /application-health page-composition boundary while leaving /api/application-health unchanged.

Added operator urgency levels distinct from technical severity: NO_ACTION_NEEDED, CHECK_WHEN_CONVENIENT, ACTION_RECOMMENDED, and GET_TECHNICAL_HELP.

Expanded the catalog to cover all six current Dashboard attention conditions: Host Connectivity FAIL/WARNING, Workflow FAIL, Automation FAIL, Remediation FAIL, and Remediation WARNING.

Added continuity fields for every guide: what happened, what it means, what it affects, safe actions, whether it can wait, how recovery is recognized, what not to do, when to get help, and a link to technical details.

Added failure-isolated page lookup through safe_for_attention() so a missing, unreadable, malformed, or invalid optional guidance catalog cannot prevent Application Operations from rendering.

Preserved strict for_attention()/load() behavior for validation and test boundaries while using the safe lookup only at the presentation boundary.

Corrected the Operational Attention markup so the attention item and technical-detail links do not create nested anchors.

Kept guidance generic where canonical topology is not established; the slice does not infer affected services merely from host naming or inventory grouping.

### Phase 16.8.3 Guidance Catalog Contract

host_connectivity_failed - Host Connectivity / FAIL / CHECK_WHEN_CONVENIENT - A system is not responding.

host_connectivity_warning - Host Connectivity / WARNING / CHECK_WHEN_CONVENIENT - A system may need attention.

workflow_failed - Workflow / FAIL / CHECK_WHEN_CONVENIENT - An automated workflow did not finish successfully.

automation_failed - Automation / FAIL / CHECK_WHEN_CONVENIENT - A scheduled HIMP task failed.

remediation_execution_failed - Remediation / FAIL / GET_TECHNICAL_HELP - A corrective action did not complete successfully.

remediation_confirmation_required - Remediation / WARNING / NO_ACTION_NEEDED - HIMP is waiting for a decision.

### Phase 16.8.3 Implementation and Release Checkpoints

Foundation implementation commit: 72fd6a023a0132848c058911433dc26c701f0e5c - feat: add operator guidance foundation.

Production markup correction commit: ef3cf6e6f15a0c4e64ce9638144e39e99951b943 - fix: avoid nested operational attention links.

Final catalog expansion and continuity hardening commit: a2452f27734d6d2c8fd797c30bbf5a23cc478478 - feat: expand operator continuity guidance.

Final implementation scope for the catalog expansion/hardening: config/operator_guidance.yml, himp/api/server.py, himp/services/operator_guidance.py, templates/application_health.html, tests/api/test_application_health_page.py, and tests/services/test_operator_guidance.py.

Focused guidance regression at the final release gate: 24 passed.

Related Application Operations regression at the final release gate: 55 passed.

Final complete HIMP regression: 1,311 passed in 6.00 seconds.

Full Python compileall: PASS.

git diff --check: PASS.

Merge-marker check: PASS.

Read-only guidance execution-safety gate: PASS.

Complete six-condition Dashboard attention mapping: PASS.

Live attention guidance coverage before release: PASS for the then-current Host Connectivity and Automation failures.

### Phase 16.8.3 Production Acceptance

The final implementation was pushed and deployed through the canonical scripts/deploy/himp.sh boundary. Release convergence was verified with LOCAL = REMOTE = DEPLOYED = a2452f27734d6d2c8fd797c30bbf5a23cc478478. HIMP and Caddy remained active, the Uvicorn listener remained on 127.0.0.1:9347, and Caddy remained on TCP 443. The deployed catalog contained exactly six validated guidance entries with affects and resolved_when fields present for every entry. All six deployed attention mappings passed. The live production operational summary at final acceptance was PASS with zero current attention items.

The first authenticated acceptance helper used an incorrect import path for require_page_session and failed before exercising the route; this was an acceptance-script defect, not an application defect. The corrected production acceptance used server.require_page_session and returned HTTP 200 from /application-health with Application Operations, Operational Attention, and Operational Navigation all present. The rendered response length was 31,475 characters. No recent HIMP error, exception, traceback, or critical log entries were found, and the repository remained clean and synchronized after acceptance.

### Phase 16.8.3 Closure Decision

Phase 16.8.3 - Operator Guidance, Self-Help & Continuity is CLOSED as COMPLETE / PRODUCTION VERIFIED. HIMP now provides a deterministic, reviewed, read-only self-help layer for every current Operational Attention condition while preserving the existing Dashboard as the authoritative attention aggregator and the owning HIMP pages as the authoritative action surfaces. Guidance failure is isolated from the Application Operations page, technical severity is separated from operator urgency, and the continuity contract explicitly tells a non-technical operator what happened, what it affects, what is safe to check, whether the condition can wait, how to recognize recovery, what not to do, and when to seek technical help.

### Next-Session Starting Point

Resume from the clean Phase 16.8.3 production checkpoint. Do not reopen Phase 16.8.1, 16.8.2, or the 16.8.3 foundation/catalog contract unless production evidence identifies a defect. The next preferred bounded continuity slice is to expand the reviewed self-help library using the canonical HIMP inventory and real production evidence. Prioritize safe operator tip sheets for current infrastructure categories and common symptoms - including DNS, Proxmox, backup/PBS, storage/NAS, HIMP, automation, vulnerability scanning, VPN, media, logging, and monitoring - without inferring topology from names or groups and without adding automatic remediation. Each guide should preserve the established continuity contract and link back to the owning HIMP evidence surface. Inspect existing inventory/plugin/relationship contracts first, implement one coherent guide family at a time, then run focused/full regression, compileall, git diff --check, production acceptance, Git checkpoint, canonical deployment, and authoritative roadmap update.

### Roadmap Decision Record - 2026-08-27 Phase 16.8.3 Closure

Phase 16.8.3 Operator Guidance, Self-Help & Continuity is COMPLETE / PRODUCTION VERIFIED. The production Application Operations page now provides deterministic self-help for all six current Dashboard Operational Attention conditions. The final deployed application revision is a2452f27734d6d2c8fd797c30bbf5a23cc478478. Final regression is 1,311 passing tests with compileall, diff, merge-marker, scope, read-only safety, catalog-contract, and attention-mapping gates passing. Corrected authenticated production acceptance returned HTTP 200 and verified Application Operations, Operational Attention, and Operational Navigation; HIMP and Caddy were active, listeners were correct, recent HIMP errors were none, live operational state was PASS with zero current attention items, and the repository was clean. Future self-help expansion should remain reviewed, deterministic, inventory-grounded, and non-remediating.

## Operational Production Record - 2026-08-30 FreePBX Onboarding and Vulnerability Baseline

Status: COMPLETE / PRODUCTION VERIFIED.

This revision records the production onboarding of the FreePBX telephony host into HIMP and the completion of its first constrained Greenbone vulnerability baseline. This was an operational use of the Phase 16 inventory and vulnerability-management capabilities, not a new parallel subsystem or a reopening of completed Phase 16 slices.

### FreePBX Production Readiness and Security Validation

FreePBX host: freepbx at 10.10.37.70 on Debian 12 (bookworm). FreePBX was brought to version 17.0.32; the running Asterisk instance was verified as 22.8.2.

The Grandstream desk phone on extension 101 was registered and operational. The extension authentication secret was rotated without recording the secret value in this roadmap.

Fail2Ban temporarily blocked the phone after the credential transition. Only the affected phone address was unbanned; registration recovered immediately. The trusted LAN/firewall posture was preserved rather than broadly weakening intrusion protection.

Functional telephony acceptance passed: the *43 echo test, normal outbound calling, inbound calling, two-way audio, trunk registration, and endpoint availability were all verified. Emergency calling was not used for testing.

The VoIP.ms PJSIP trunk remained registered and reachable after the changes.

AMI remained bound to localhost and the database account remained local-only. Previously exposed internal credentials were not reproduced in documentation and were not rotated solely for documentation purposes because doing so would create unnecessary production risk.

FreePBX module/security maintenance was completed through supported FreePBX tooling. FreePBX-held operating-system packages were left held; no broad package upgrade or forced held-package change was performed.

A logrotate failure was traced to the systemd MemoryDenyWriteExecute restriction conflicting with PHP PCRE JIT during FreePBX/Asterisk postrotate processing. A targeted systemd override set MemoryDenyWriteExecute=false for logrotate.service; logrotate subsequently completed successfully and the daily timer remained active.

A controlled reboot completed successfully. The host returned with the expected kernel, telephony services and registrations recovered, Fail2Ban remained healthy, and failed systemd units were cleared.

### HIMP Inventory Onboarding

A dedicated telephony inventory group was added rather than placing FreePBX under maintenance. This keeps the PBX outside the scheduled package-maintenance authorization path while still making it a first-class HIMP inventory asset.

The FreePBX inventory record uses hostname freepbx, address 10.10.37.70, SSH user root, category Telephony, role PBX, platform Debian, vendor FreePBX, priority Critical, and selective reporting.

Git checkpoint 2d8c28762d826c4c09806007049e7e6d0c3945d8 (feat: add FreePBX to telephony inventory) added inventory/group_vars/telephony.yml and the FreePBX host entry. LOCAL and REMOTE matched at that revision.

Canonical deployment correctly preserved the persistent runtime inventory. Because telephony was a new group and the runtime inventory writer cannot create groups, the source and runtime inventories were compared before activation. The only source/runtime host delta was FreePBX; no existing runtime host differed.

A timestamped backup of the persistent runtime inventory was created, the approved Git inventory and telephony group variables were installed into the runtime inventory, and the runtime inventory was validated as the himp service identity.

The production inventory synchronization completed successfully with 48 active hosts and 52 total known hosts, an increase of exactly one host from the prior 47 active / 51 total state.

Production PostgreSQL verification confirmed FreePBX as an active inventory record in group telephony at 10.10.37.70. HIMP remained active after synchronization.

### Greenbone Onboarding and Baseline Scan

The canonical Greenbone manifest /etc/himp-greenbone/scan-hosts.tsv was updated with exactly one FreePBX entry. Duplicate hostname and address checks both returned one entry.

The existing constrained HIMP Greenbone integration was used; arbitrary GMP access, Greenbone task ownership changes, and scanner self-targeting were not introduced.

host-reconcile created target HIMP - freepbx and task HIMP - freepbx - Full and Fast. Target UUID: c3b9778c-91df-4a00-aa1d-261ebe8e7ba9. Task UUID: 5d6303d3-36f6-4111-81da-621c5ae25d65.

The scan used the established Full and fast configuration, OpenVAS Default scanner, and All TCP and Nmap top 100 UDP port list.

host-start successfully started the bounded FreePBX scan. Report UUID: 71c9182c-bb7f-415a-b795-eaffe772b477.

Live scanner evidence proved the scan was genuinely executing against 10.10.37.70, including OpenVAS processes, nmap.nasl activity, a full TCP-port sweep plus the selected UDP set, and packet captures from the scanner container to FreePBX.

The scan started at 2026-08-30 16:29:48 UTC and completed at 2026-08-30 18:21:57 UTC, approximately 1 hour 52 minutes later, with progress 100 and processing_required=0.

The completed Greenbone report contained 3 result rows. All three were Log/Info findings with maximum severity 0.0. No positively scored Low, Medium, High, or Critical result rows were present in this baseline report.

The severity result is encouraging but is not documented as proof that the host can never contain vulnerabilities; it records the evidence returned by this specific completed Greenbone baseline and scan configuration.

### HIMP Vulnerability Intelligence Acceptance

The completed FreePBX report was discovered through the installed HIMP Greenbone identity and was present in the HIMP vulnerability persistence layer.

Production verification reported REPORT_PRESENT=True and FINDING_COUNT=3 for the FreePBX report.

The existing authenticated Vulnerability Intelligence host/report/finding routes are the owning presentation surfaces for this evidence. No duplicate vulnerability database or alternate report store was created.

This operational exercise validates the intended Phase 16 architecture end-to-end: HIMP inventory defines the host, the constrained Greenbone boundary reconciles and scans it, completed evidence is imported into HIMP, and operators can review the resulting host/report/finding evidence through HIMP.

### Operational Decisions and Follow-Up

FreePBX remains outside the maintenance group. Any future package or PBX upgrade automation must be explicitly designed for telephony continuity rather than inherited from generic maintenance authorization.

Do not weaken Fail2Ban or the FreePBX firewall to avoid future credential-transition bans. Use targeted unban/recovery and preserve the trusted-LAN boundary.

Do not manually edit FreePBX-generated configuration files. Continue to use supported FreePBX interfaces and fwconsole workflows for configuration regeneration.

Continue using the HIMP per-host Rescan capability and constrained Greenbone integration for future FreePBX verification scans rather than changing Greenbone ownership or exposing arbitrary scanner controls.

A future FreePBX rescan can establish historical comparison once additional completed reports exist. The existing Phase 16.6 comparison/export capability should be reused.

A separate low-priority engineering follow-up remains for standalone HIMP CLI PostgreSQL pool-cleanup warnings observed after successful inventory queries; this did not block FreePBX onboarding or vulnerability ingestion.

### Next-Session Starting Point

Resume from the completed FreePBX production baseline. Do not reopen the FreePBX onboarding or baseline scan unless new production evidence identifies a defect. For HIMP product development, continue from the Phase 16.8.3 checkpoint and expand reviewed, deterministic continuity guidance one bounded guide family at a time. For FreePBX operations, use HIMP Vulnerability Intelligence as the evidence surface and perform a future bounded rescan when there is a meaningful remediation, software change, or scheduled verification need so Phase 16.6 historical comparison can show change over time.

### Roadmap Decision Record - 2026-08-30 FreePBX Operational Baseline

FreePBX production onboarding and vulnerability baseline are COMPLETE / PRODUCTION VERIFIED. The PBX is operational, security maintenance and credential rotation were completed without weakening the security boundary, the host is persisted in HIMP under the dedicated telephony group, and the production inventory now contains 48 active hosts / 52 total known hosts. Git inventory revision 2d8c28762d826c4c09806007049e7e6d0c3945d8 was pushed and deployed through the canonical release boundary; persistent runtime inventory was deliberately preserved and then explicitly synchronized after a source/runtime comparison proved FreePBX was the only delta. Greenbone target/task reconciliation and a bounded Full and Fast scan completed successfully under report 71c9182c-bb7f-415a-b795-eaffe772b477. The report contained three informational findings at maximum severity 0.0 and no positively scored vulnerability findings. HIMP persistence confirmed the report and all three findings. The existing Phase 16 inventory, constrained Greenbone, vulnerability persistence, and operator UX contracts therefore worked together successfully for a newly onboarded critical telephony asset.

## Phase 16.8.3A — Inventory-Aware Operator Guidance

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 16.8.3A extends the reviewed, deterministic operator-guidance foundation with inventory-aware host-connectivity guidance. The implementation preserves the existing generic guidance contract while selecting more specific continuity guidance only when structured affected-host evidence supports one known operational domain. When evidence is missing, malformed, unknown, or spans multiple domains, HIMP deliberately falls back to the generic host-connectivity guidance rather than guessing.

### Implementation and Safety Contract

Dashboard Operational Attention now preserves bounded affected-host evidence for host connectivity FAIL and WARNING conditions using only hostname, inventory group, and IP address.

OperatorGuidanceService uses a centralized deterministic host-domain classifier rather than hostname-specific rules or a duplicate inventory parser.

Reviewed domain-specific guidance is available for DNS, backup, virtualization, media, VPN, and telephony. DNS covers the canonical pihole, technitium, and unbound inventory groups; the other supported domains map to their coherent canonical inventory groups.

The guidance catalog contains 18 reviewed entries in production, including the existing generic attention guidance plus domain-specific host-connectivity FAIL/WARNING guidance.

Same-domain multi-host evidence can select the matching domain guidance. Mixed-domain evidence, unknown groups, missing evidence, malformed evidence, and incomplete affected-host records fail closed to the generic host-connectivity guidance.

The implementation does not classify the heterogeneous infrastructure or management groups as one operational domain. Richer guidance for HIMP, databases, logging, vulnerability scanning, monitoring, storage, and similar systems remains deferred until authoritative operational metadata can support the classification without hostname guessing.

No automatic remediation, arbitrary Greenbone control, topology inference, or AI-generated operator advice was introduced. Guidance remains Git-managed, reviewed, deterministic, read-only, and designed for safe nontechnical continuity.

### Regression and Production Acceptance

Final full regression baseline: 1330 passing tests.

Verified application release: 2e674dd5bd5f8911934e4ddf49980adbc41c15ed.

Production release marker matched the expected release exactly and himp.service remained active before and after functional validation.

Production loaded exactly 18 operator-guidance catalog entries.

Live production classification passed for DNS FAIL/WARNING, backup FAIL, virtualization FAIL, media FAIL, VPN FAIL, and telephony FAIL/WARNING, including the expected reviewed urgency for each tested condition.

Same-domain multi-host DNS classification passed.

Mixed-domain evidence fell back to host_connectivity_failed as designed.

Unknown-group evidence fell back to host_connectivity_failed as designed.

Missing-evidence input fell back to host_connectivity_failed as designed.

The application remained responsive after validation; the root application request returned HTTP 303 and the service state remained active.

### Phase 16.8.3A Closure Decision

Phase 16.8.3A is CLOSED as COMPLETE / PRODUCTION VERIFIED. The production behavior now provides more useful continuity guidance when authoritative inventory evidence identifies a supported operational domain, while preserving a conservative generic fallback everywhere the evidence is insufficient. This closes the bounded inventory-aware expansion without weakening the Phase 16.8.3 safety model or creating a parallel inventory/classification architecture.

### Next-Session Starting Point

Resume from verified production release 2e674dd5bd5f8911934e4ddf49980adbc41c15ed. Do not reopen Phase 16.8.3A unless new production evidence identifies a defect. Before adding guidance for heterogeneous infrastructure or management assets, inspect the existing persisted inventory model and repository contracts to determine whether authoritative service, role, category, or other operational-domain metadata already survives into runtime inventory records. If that metadata is insufficient, keep those assets on generic guidance until an explicit canonical metadata enhancement is designed; do not introduce hostname heuristics or a second inventory parser.

### Roadmap Decision Record - 2026-09-19 Phase 16.8.3A Closure

Phase 16.8.3A Inventory-Aware Operator Guidance is COMPLETE / PRODUCTION VERIFIED at application release 2e674dd5bd5f8911934e4ddf49980adbc41c15ed with a 1330-test full regression baseline. Production validated an 18-entry reviewed guidance catalog, domain-specific continuity guidance for DNS, backup, virtualization, media, VPN, and telephony, same-domain multi-host classification, and fail-safe generic fallback for mixed-domain, unknown-group, and missing evidence. HIMP remained active and responsive after the validation. Heterogeneous infrastructure and management classifications remain intentionally generic until authoritative operational metadata supports safe deterministic specialization.

## Phase 16.8.4 — Continuity Metadata & Service Dependency Model

Status: COMPLETE / PRODUCTION VERIFIED.

Phase 16.8.4 establishes the first deployment-neutral continuity data model that translates HIMP’s existing asset relationship graph into reviewed household operational meaning. The slice is intentionally read-only and conservative: it reuses the canonical relationship subsystem, keeps continuity metadata separate from topology, refuses to infer missing relationships, and exposes unclassified dependency impact rather than manufacturing continuity meaning.

### Architecture and Product Contract

Reused the existing asset relationship subsystem as the single topology model. No second dependency or continuity-topology store was created.

Added Git-managed config/continuity_metadata.yml for deployment-specific, reviewed continuity meaning. The core contract remains deployment-neutral; host identity, household impact, priorities, and operator authority enter through configuration rather than hard-coded product assumptions.

Continuity metadata uses the same (entity_type, entity_id) identity contract as asset relationships and records display_name, continuity_role, criticality, household_impact, recovery_authority, and can_wait.

The metadata contract contains no credentials, passwords, SSH commands, IP-address-driven recovery logic, or recovery procedures. Infrastructure relationships remain in config/infrastructure_relationships.yml and operator instructions remain in config/operator_guidance.yml.

ContinuityMetadataService validates supported entity types, required non-empty fields, criticality, recovery authority, configuration structure, and duplicate entity identities. Invalid configuration fails closed.

Criticality ordering is centralized in ContinuityMetadataService and reused by ContinuityImpactService rather than duplicated.

ContinuityImpactService combines reverse dependency impact with reviewed continuity metadata. It reports reviewed affected assets, unclassified impacted assets, counts for both, root metadata, and the highest reviewed criticality without inferring meaning for unreviewed entities.

The default continuity metadata path is config/continuity_metadata.yml, allowing normal production service construction while retaining explicit path injection for tests and alternate deployments.

### Initial Reviewed Continuity Catalog

Six reviewed continuity entities were established: application:himp, database:himp, host:automation.server.arpa, host:himpdb01.server.arpa, service:home_telephone, and host:freepbx.

HIMP, its database, and their two hosts are classified as important management/guidance infrastructure with technical_only recovery authority. Their loss can remove HIMP visibility or management capability without automatically implying failure of the household systems HIMP monitors.

Home Telephone is classified as a critical essential_household_service with technical_only recovery authority.

FreePBX is classified as critical essential_service_infrastructure with technical_only recovery authority. The reviewed continuity text directs a nontechnical operator to seek technical help rather than changing trunks, extensions, routes, or SIP configuration.

A reviewed relationship was added: service:home_telephone runs_on host:freepbx. This is an explicitly known production relationship, not an inference from inventory naming or grouping.

### Safety Hardening Included in the Slice

OperatorGuidanceService host-domain classification was hardened to fail closed when affected_hosts is empty, malformed, contains non-mapping entries, or contains any host without a valid non-empty group.

Partially malformed host evidence now falls back to generic host-connectivity guidance instead of allowing the remaining valid entry to select domain-specific guidance.

Continuity impact preserves unknown/unreviewed graph entities in an explicit unclassified collection so missing reviewed metadata is visible rather than silently discarded.

The slice remains informational and read-only. It adds no automatic recovery, reboot, restart, shell, SSH, Ansible, firewall, DNS, virtualization, Greenbone, or FreePBX mutation authority.

### Deliberate Topology Deferrals

DNS continuity topology remains deferred. The production environment has multiple Unbound, Technitium, and Pi-hole systems and the current graph does not yet represent redundant OR-style service dependencies. Modeling every resolver as a hard dependency would falsely imply a household DNS outage when one redundant provider fails.

Backup continuity topology remains deferred because multiple backup platforms and protected systems exist without a sufficiently reviewed job/datastore/service relationship model.

Storage, media/photo, and other heterogeneous infrastructure relationships remain deferred until authoritative dependency evidence exists.

Criticality is not treated as urgency. A critical service can remain available when a redundant provider fails; future wife-facing continuity state must combine reviewed service importance with actual service state and redundancy evidence.

### Validation and Production Acceptance

Targeted Phase 16.8.4 regression completed with 108 passing tests after the continuity metadata, continuity impact, operator-guidance hardening, and asset-relationship changes.

Continuity catalog validation passed for all six reviewed entities, including critical Home Telephone and FreePBX classifications and technical_only recovery authority.

Before the application release, the production relationship database was reconciled through the existing AssetRelationshipService boundary rather than direct SQL manipulation. The intended change was one addition: service:home_telephone runs_on host:freepbx; existing HIMP relationships were preserved.

Production continuity validation confirmed the existing HIMP dependency chain and the FreePBX/Home Telephone continuity chain using the production PostgreSQL-backed relationship service.

Implementation commit: 0e235f94e307c0c5502ac055115fea990da953eb — feat: add continuity impact model.

Implementation scope: 9 files changed, 1,599 insertions, 9 deletions; new continuity metadata and impact services plus tests, relationship configuration, and operator-guidance hardening.

The implementation commit was pushed and deployed through scripts/deploy/himp.sh. Release convergence was verified as LOCAL = REMOTE = DEPLOYED = 0e235f94e307c0c5502ac055115fea990da953eb.

After deployment, himp.service was active and the application readiness check succeeded. The repository remained clean and synchronized.

### Phase 16.8.4 Closure Decision

Phase 16.8.4 — Continuity Metadata & Service Dependency Model is CLOSED as COMPLETE / PRODUCTION VERIFIED. HIMP now has a reviewed, deployment-specific continuity metadata layer that composes with the existing canonical asset relationship graph without duplicating topology or inventing dependencies. The first critical household service relationship—Home Telephone through FreePBX—is represented and production validated, while ambiguous redundant services remain deliberately unmodeled until authoritative evidence exists.

### Product Direction Preserved

All subsequent continuity work must satisfy two goals concurrently: improve safe nontechnical household continuity and preserve HIMP as a deployment-neutral product. HIMP Core must contain no deployment-specific assumptions. Homelab-specific identity, topology, policy, contacts, credentials, continuity meaning, and integrations must enter through configuration, inventory, secrets, relationships, or plugins. Public/Docker distribution must exclude private hostnames, addresses, credentials, certificates, contacts, scan results, databases, and household-specific continuity documents.

### Next-Session Starting Point

Resume from clean production release 0e235f94e307c0c5502ac055115fea990da953eb. Do not reopen Phase 16.8.4 unless new production evidence identifies a defect. The next continuity slice should build on the new metadata/relationship foundation toward a simplified Continuity Dashboard / “What do I need to do?” experience, while keeping technical detail secondary, grouping downstream symptoms around reviewed root causes, and preserving fail-closed behavior. Continue expanding continuity metadata and relationships only where authoritative production evidence exists; do not infer DNS, backup, storage, or other redundant service topology from inventory groups alone.

### Roadmap Decision Record - 2026-09-19 Phase 16.8.4 Closure

Phase 16.8.4 is COMPLETE / PRODUCTION VERIFIED at application release 0e235f94e307c0c5502ac055115fea990da953eb. The phase introduced the Git-managed continuity metadata contract, deterministic ContinuityMetadataService and ContinuityImpactService, explicit unclassified-impact reporting, a reviewed Home Telephone → FreePBX dependency, and stricter fail-closed inventory-aware operator guidance. The architecture continues to use asset_relationships as the sole topology system and deliberately defers ambiguous redundant-service modeling. This establishes the data foundation for a future nontechnical continuity mode without embedding this homelab’s private assumptions into HIMP Core.